## KONTi Dashboard Feedback
ID | Source | Area / Module | Issue Description | Requested Change / Fix | Priority | Priority Rationale | Proposed Fix | Effort | ETA | Owner | Status | Scope | Scope Rationale
Project Detail — Casa Solar Rincón
A-01 | Changelog PDF | Project Detail > Financials | No per-invoice columns for client view (total amount, paid, balance, invoice status). | Add columns: Monto Total, Pagado, Saldo Pendiente, Estado per invoice on the client-facing financial tab. | High | Requested explicitly; clients need billing transparency without contacting the team. | Extend the client-view financial table with four new columns pulled from the existing invoice data model. Add color-coded status badge (Pagada / Pendiente / Vencida). | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 explicitly shows 'Estado de facturas / saldo pendiente' and Cost-Plus model tracking as part of the construction phase dashboard. ¦ Done in #99 (Reviewer feedback bundle #2): project-invoices.tsx Total/Paid/Balance/Status columns now render from invoice data.
A-02 | Changelog PDF | Project Detail > Financials | No 'Gastos no facturables' (non-billable expenses) tab exists. | Add a dedicated 'Gastos no facturables' tab to the project financials section. | Medium | Explicitly requested; needed for accurate internal cost tracking vs. client billing. | Add a new tab in the project financials panel. Create a simple CRUD table for non-billable line items (description, amount, date, category). Include subtotal at the bottom. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | Done | V2 – Out of Scope | The workflow covers client-facing billing (Cost-Plus invoicing) but does not include an internal non-billable expense tracking module. Defer to V2 for advanced accounting features. ¦ Done + verified 2026-05 (Task #157): the 'Non-Billable Expenses' / 'Gastos no facturables' tab is rendered by artifacts/konti-dashboard/src/components/cost-plus-budget.tsx (L51-L171) inside the Cost-Plus budget card on the project detail page, with category badge, date, description, payer, amount, and a 'Non-Billable Total' / 'Total no facturable' subtotal. Data comes from the existing PROJECT_COST_PLUS API (cp.nonBillableExpenses + cp.nonBillableTotal). The original ask was a display tab; in-dashboard CRUD authoring is tracked separately if KONTi wants it later.
A-03 | Changelog PDF | Project Detail > Documents | Client cannot upload files; it is unclear whether they can and in which section. | Enable client-side document upload or clearly define the upload policy and location. | High | Repeated across multiple sessions; missing client upload capability blocks collaboration. | Add an 'Upload Document' button to the client view of the Documents tab. Restrict to PDF/image formats. Store in the project's document store with a 'Client Upload' tag visible to the team. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 requires 'El cliente brinda firmas y documentos requeridos' — client document upload is a core V1 requirement for permit authorization. ¦ Done in #61 (client portal expansion: client uploads enabled).
A-04 | Changelog PDF | Project Detail > Documents | Documents are flat; no 'Contratos y Acuerdos de compra' grouping exists. | Organize the 'Acuerdos' category into a 'Contratos y Acuerdos de compra' sub-group. | Medium | Explicitly requested; improves document discoverability for legal/procurement docs. | Add a document-category taxonomy. Create a 'Contratos y Acuerdos de compra' category in the document type selector. Migrate existing Acuerdos documents to the new category. | Low | Sprint 1–2 (1–2 wks) | Frontend + Backend | Done | V1 – In Scope | Fases 3.1–3.3 list Contrato and Documentos as explicit deliverables per phase. Document categorization is required to support this multi-phase document structure. ¦ Done in #63 (document organization: contracts/agreements grouping).
A-05 | Changelog PDF | Project Detail > Documents | No version history for documents; only the latest version is accessible. | Keep the latest version downloadable but maintain a history of all versions. | Medium | Explicitly requested; essential for audit trail on contracts and permits. | Implement document versioning: store each upload as a new version, display a version history dropdown, allow download of any prior version. Show 'Latest' badge on current version. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | Done | V2 – Out of Scope | The workflow does not reference document versioning or audit trails. Basic document upload/download is V1; full version history is an advanced document management feature for V2. ¦ Done in #158: documents now support a 'New version' upload — POST /api/projects/:projectId/documents/:documentId/versions appends a versions[] entry, rolls primary fileSize/uploadedAt forward (uploadedBy is intentionally preserved as the immutable original-uploader handle the A-09 dual gate checks), and emits a `document_version_added` activity (artifacts/api-server/src/routes/projects.ts L749+). The project-detail DocCard renders a team-only Upload icon next to each doc row that picks a file and calls useAppendProjectDocumentVersion. File-content storage continues to flow through the existing Drive sync layer in production / static seed images in dev — this endpoint records version metadata only, matching every other document upload path in the dashboard.
A-06 | Changelog PDF | Project Detail > Documents | Team cannot control which documents are visible to the client. | Allow team to mark documents as 'Private' (team-only) vs. visible to client. | High | Repeated; team needs to share selectively — internal docs must never reach the client by default. | Add a 'Visibility' toggle (Private / Client) on each document row. Default new uploads to Private. Filter client document view to show only Client-visible documents. | Low | Sprint 1–2 (1–2 wks) | Frontend + Backend | Done | V1 – In Scope | The workflow distinguishes between internal team documents and client-facing deliverables across all phases. Document visibility control is a core V1 requirement. ¦ Done in #61 (per-document client visibility) and reinforced by #88 (client ownership checks).
A-07 | Changelog PDF | Project Detail > Photos & Media | No photos, video, or photo-comment section exists inside the project. | Add a Photos & Comments section where team and client can upload and annotate site photos. | High | Mentioned 4 times across different pages; core project communication feature. | Create a 'Fotos & Medios' tab in the project detail. Support image/video upload with caption and date. Allow threaded comments per photo. Link photos to punchlist items. | High | Sprint 3 (3–5 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 explicitly lists 'inspecciones, reportes, de avance y seguimiento de contratistas' delivered to the client. Site photos are a core part of construction progress reporting. ¦ Done in #105 (Site photos: upload, categorize, link them from the project report).
A-08 | Changelog PDF | Project Detail > Client Settings | Client profile settings lack phone number, postal address, and physical address fields. | Add phone, dirección postal, and dirección física to the client configuration section. | Medium | Explicitly requested; needed for client communications and permit filings. | Add three new fields to the client settings form: Teléfono, Dirección Postal, Dirección Física. Persist to the client profile model. | Low | Sprint 1 (< 1 wk) | Frontend + Backend | Done | V1 – In Scope | Client profile data is required for permit documentation (Fase 4) and contract generation (Fases 2–3). Address and phone fields are basic CRM data captured in Fase 1. ¦ Done in #75 (ClientContactCard with phone, postal, physical addresses).
A-09 | Changelog PDF | Project Detail > Client Settings | Images/media in the project are not self-manageable by the client. | Allow clients to self-administer and upload images within the project. | Medium | Explicitly requested; reduces team bottleneck for media management. | Grant clients upload permission on the Photos & Media tab. Add a client-facing media management panel with upload, delete (own uploads only), and caption-edit capabilities. | Medium | Sprint 3 (3–5 wks) | Frontend | Done | V2 – Out of Scope | The workflow shows the client as a recipient of reports and a signer of documents, not as a media manager. Full client-side media self-administration goes beyond the V1 portal scope. ¦ Done in #158: PATCH /api/projects/:projectId/documents/:documentId now accepts a `caption` field with a 500-char cap behind a dual gate — team/admin/superadmin can edit any document, clients can edit ONLY captions on documents they themselves uploaded (artifacts/api-server/src/routes/projects.ts L584-L745). The site-photos gallery renders Pencil/Trash buttons on each owned thumbnail (artifacts/konti-dashboard/src/components/site-photos-gallery.tsx) so clients can rename or remove their own uploads inline.
A-10 | Changelog PDF | Project Detail > Phases / Timeline | Parallel phases are not supported; the timeline assumes sequential phases only. | Clarify or implement support for phases running in parallel. | Info | Needs a product decision on whether to show a Gantt-style view or a parallel-phase indicator. | Product decision required: define parallel-phase UX (Gantt bars vs. split-phase cards). Once decided, implement phase-overlap data model and update the timeline visual. | High | TBD (needs spec) | Product + Frontend | Done — decision only | V1 – In Scope | The workflow header explicitly states 'las fases pueden ir en paralelo'. Parallel phase support is a V1 requirement. The Gantt visualization style is the open decision, not the parallel concept itself. ¦ Decision logged in #160 (Parallel phases — keep current model). Investigation confirms the existing two-tier model already covers the ask: macro-phases (lead → consultation → pre_design → schematic_design → design_development → construction_documents → permits → construction → completed) are deliberately serial because each transition is gated by signatures, payments, OGPE authorization, and a punchlist (artifacts/api-server/src/data/seed.ts PHASE_ORDER ~L1705-L1715; gating logic in artifacts/api-server/src/routes/projects.ts /advance-phase ~L1485-L1511 — open-punchlist gate, client-only consultation gate, idx-based forward step), while inside the construction macro-phase the six milestones (foundation, framing, roofing, MEP, finishes, final) carry independent startDate/endDate/status values and render as a Gantt-style overlapping timeline (artifacts/api-server/src/data/seed.ts PROJECT_MILESTONES ~L2386-L2405; artifacts/konti-dashboard/src/components/milestones-timeline.tsx gantt-track / gantt-bar). Net: parallelism is supported where it actually happens (construction work-streams), and the serial macro-chain stays intact because relaxing it would bypass the signature/payment gates the build depends on. No code change. Decisión registrada en #160 (Fases paralelas — mantener modelo actual): los macro-fases siguen siendo seriales por las puertas de firma/pago/punchlist, mientras los hitos de construcción ya corren en paralelo dentro de la fase de Construcción.
A-11 | Changelog PDF | Project Detail > Contractor Report | Contractor monitoring report lacks a consolidated view of delays, weather, issues, change orders, non-compliance, and rework. | Expand the contractor monitoring report to include all of the above data points. | High | Explicitly requested; partially addressed by existing tasks but a unified report view is still missing. | Consolidate weather data, change orders, punchlist items, and phase notes into a single 'Contractor Monitoring' report section. Add filters by date range and category. Export to PDF. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | Done — needs verification | V1 – In Scope | Fase 5 explicitly lists 'seguimiento de contratistas, cumplimiento de contratos, incumplimientos' as deliverables to the client. Contractor monitoring is a core V1 construction-phase feature. ¦ Likely closed by #62 + #75 (Contractor Estimate Rollup on the project report); needs PM eyes-on confirmation that the consolidated view matches the original ask.
A-12 | Changelog PDF | Project Detail > Client Audit Log | No audit log of client actions on the platform. | Add a section logging all client actions (logins, uploads, messages, approvals). | Medium | Explicitly requested; important for accountability and dispute resolution. | Implement a server-side event log for client sessions. Surface a read-only 'Client Activity Log' table in the team admin view. | Medium | Sprint 3 (3–5 wks) | Backend + Frontend | Done | V2 – Out of Scope | The workflow does not include an audit log module. This is a compliance/governance feature that adds significant backend complexity beyond the V1 portal scope. Defer to V2. ¦ Done in #61 hardening + verified 2026-05 (Task #156): client-side audit log shipped — backend GET /api/projects/:id/audit-log accepts the client role behind enforceClientOwnership with a `?clientOnly=true` filter (artifacts/api-server/src/routes/projects.ts ~L2386), and the bilingual ClientActivityCard is mounted on the project detail page (artifacts/konti-dashboard/src/components/client-activity-card.tsx + project-detail.tsx ~L1721) with a Show-all / Client-only toggle. Non-owner 403 + owner 200 paths covered by client-ownership.test.ts L382-L420 (pre-existing — no new test was needed in this task).
A-13 | Changelog PDF | Project Detail > Design / Branding | Dark gray color used in the project detail is too dark; does not match KONTi brand gray. | Replace the dark gray with the KONTi brand gray from the design guide. | Low | Design polish; mentioned alongside a Drive color reference. | Update the CSS design token for the primary gray (--color-gray-dark) to the KONTi brand value. Apply across all project-detail components. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Brand consistency is a baseline requirement for any client-facing V1 portal. This is a simple CSS token change with no scope implications. ¦ Done in #62 (KONTi brand pass) and #74 (header text readable on bright cover photos).
Cost Calculator
B-01 | Changelog PDF | Cost Calculator > CSV Import | Importing the team's initial estimate CSV fails because column format does not match the calculator's expected schema. | Fix CSV import so it accepts the team's existing estimate spreadsheet format. | High | Explicitly requested; blocks the primary data-entry workflow for estimates. | Add a CSV column-mapping step to the import flow: detect headers, let the user map source columns to calculator fields, then validate and import. Provide a downloadable template CSV. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 3 includes 'Herramientas de estimación de costos' and 'Envío de comparación real vs. estimado'. The cost calculator with CSV import is a core V1 estimation tool. ¦ Done in #75 (CSV header aliases: Description, UnitPrice, etc.).
B-02 | Changelog PDF | Cost Calculator > Labor Model | Labor is calculated hourly, but the team works on lump-sum contracts. | Support lump-sum (suma alzada) labor entries in addition to hourly rates. | High | Core data-model mismatch; current hourly model creates confusion and incorrect totals. | Add a 'Labor Type' toggle per line item: Hourly (rate × hours) vs. Lump Sum (fixed amount). Update calculator totals and variance reports to handle both types. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | Done | V1 – In Scope | Fase 5 specifies 'Ejecución de obra bajo modelo Cost-Plus'. Accurate labor cost modeling (including lump-sum) is required for the Cost-Plus execution model in V1. ¦ Done in #158: Hourly vs Lump Sum labor classification shipped — ContractorEstimateLine grew an optional `laborType: 'hourly' ¦ 'lump'` (artifacts/api-server/src/routes/estimating.ts L71-L86); PUT /contractor-estimate/lines now reads/preserves it, and when category==='labor' && laborType==='lump' it forces qty=1 unit='lump' so lineTotal === lump sum and the variance report's amount-delta math is honest. The dashboard contractor-calculator edit table renders a Hourly/Lump Sum select on labor lines, mirrors the qty/unit normalisation client-side, disables qty/unit while lump is active, and shows a 'Lump'/'Global' badge in read-only view.
B-03 | Changelog PDF | Cost Calculator > Materials | Materials do not auto-populate from the project; all materials must be entered manually. | Materials should auto-populate and be reflected automatically in the calculator. | High | Explicitly requested; manual re-entry is error-prone and time-consuming. | Link the Materials Library to the calculator: when a material is added to a project, auto-create a corresponding calculator line item. Allow manual override of quantity and unit price. | Medium | Sprint 2–3 (3–4 wks) | Backend + Frontend | Done | V1 – In Scope | Fase 3.1 lists 'Materiales' and 'Presupuesto' as explicit design-phase deliverables. Auto-populating materials in the cost calculator is required for accurate V1 estimates. ¦ Done in #75 (calculator auto-populates from imported materials).
B-04 | Changelog PDF | Cost Calculator > Base Price | Base price and quantity fields are not editable in the calculator. | Allow editing of base price and quantity directly in the calculator. | High | Explicitly requested; without editable fields the calculator is read-only and unusable for estimates. | Make base price and quantity cells inline-editable. Add input validation (positive numbers only). Persist changes to the project's estimate record. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | The cost calculator is a core V1 tool (Fase 3). Editable price/quantity fields are a fundamental requirement for any functional estimator. ¦ Done in #75 (inline edit + PATCH /projects/:id/calculations/:lineId persistence).
B-05 | Changelog PDF | Cost Calculator > Contractor Info | Contractor section shows project-level info (sq ft, bathrooms, contingency) instead of contractor-specific data. | Separate contractor data from project metadata; show contractor-specific fields in the contractor section. | Medium | UX confusion; mixing project info with contractor info leads to data entry errors. | Refactor the contractor section to show only contractor-specific fields (name, rate, scope). Move project metadata to a dedicated 'Project Info' card. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 tracks contractor execution under the Cost-Plus model. Correct separation of contractor vs. project data is required for accurate V1 cost tracking. ¦ Done in #75 (Project Information panel with bathrooms/kitchens/margin/mgmt-fee inputs).
B-06 | Changelog PDF | Cost Calculator > Summary View | Calculator output does not show organized sections and summaries by category. | Display the estimate with sections and category subtotals matching the team's existing estimate format. | High | Explicitly requested; the current flat list makes it hard to review estimates with clients. | Group calculator line items by category (Design, Materials, Labor, Permits, Taxes & Gov Fees, Contingency). Show a subtotal per category and a grand total. | Medium | Sprint 2 (2–3 wks) | Frontend | Done | V1 – In Scope | Fase 3 includes client-facing budget presentation ('Presentación de 3 propuestas + presupuesto estimado'). A categorized summary view is required for client proposal presentations. ¦ Done in #99 (Reviewer feedback bundle #2): calculator estimate table now groups by category with per-category subtotal cards, mirroring the team's external estimate format.
B-07 | Changelog PDF | Cost Calculator > Imports Section | It is unclear whether the 'imports' line reflects the materials section or a separate cost category. | Clarify what 'imports' represents and ensure it is reflected correctly in the estimate. | Medium | User confusion; ambiguous label leads to incorrect cost categorization. | Rename 'imports' to a clear label (e.g., 'Imported Materials / Shipping'). Add a tooltip explaining the category. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Label clarity in the cost calculator is a V1 UX requirement. This is a minor copy/tooltip fix that supports accurate estimate presentation. ¦ Done in #99 (Reviewer feedback bundle #2): renamed Imports tab to 'Imported Materials' / 'Materiales Importados' with hover tooltip describing CSV/Excel bulk import.
B-08 | Changelog PDF | Cost Calculator > Effective Rate | It is unclear what 'effective rate' means in the calculator. | Clarify or remove the 'effective rate' field; add a tooltip or explanation. | Low | Minor UX confusion; a tooltip or label change resolves it. | Add an info tooltip to the 'Effective Rate' field explaining the formula. If the field is unused, remove it from the UI. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor UX polish on an existing V1 calculator field. No new feature scope required. ¦ Done in #75 (renamed to 'Effective Price' with tooltip + legend).
B-09 | Changelog PDF | Cost Calculator > Receipts / Variance | The variance tab is hard to find; users cannot easily navigate to receipts and categorize them. | Surface the variance/receipts tab from the dashboard so users do not need to navigate deep into the project. | Medium | Explicitly requested; discoverability issue reduces adoption of the receipts feature. | Add a 'Receipts & Variance' shortcut card on the project dashboard. Deep-link directly to the calculator variance tab. Add breadcrumb navigation. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | Fase 3 includes 'Envío de comparación real vs. estimado'. The receipts/variance tab is a core V1 feature; improving its discoverability is a V1 navigation fix. ¦ Done in #99 (Reviewer feedback bundle #2): added 'Receipts & Variance' shortcut card on dashboard linking team users straight to /calculator?tab=variance.
B-10 | Changelog PDF | Cost Calculator > Receipts / Variance | Receipts and contractor estimates do not persist across server restarts (in-memory only). | Persist receipts and contractor estimates to the database so they survive restarts. | Critical | Data loss bug; any server restart wipes all entered receipt data. | Migrate receipt and contractor-estimate storage from in-memory to the persistent database. Add a migration script for existing demo data. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V1 – In Scope | Data persistence is a fundamental V1 infrastructure requirement. This is a critical bug fix, not a new feature. ¦ Done in #27 (receipts and contractor estimates persist across restart).
B-11 | Changelog PDF | Cost Calculator > Receipt OCR | Receipt OCR is mocked; real PDF/image extraction is not implemented. | Replace mocked OCR with real PDF/image text extraction for receipts. | High | Explicitly requested; mocked OCR produces unreliable data and erodes trust. | Integrate a real OCR service (e.g., AWS Textract or Google Document AI) for receipt PDF/image uploads. Parse vendor, date, line items, and total. | High | Sprint 2–3 (3–4 wks) | Backend | Done | V2 – Out of Scope | The workflow does not specify automated OCR for receipts. Manual receipt entry or upload is sufficient for V1. Real OCR integration is a significant third-party dependency best deferred to V2. ¦ Done in #28 (real PDF/image OCR replaces the mock).
B-12 | Changelog PDF | Cost Calculator > Report Template | PDF export does not use the saved report template; it generates a generic layout. | Use the saved report template when exporting project PDFs from the calculator. | High | Explicitly requested; clients receive inconsistently formatted reports. | Load the project's saved report template (logo, colors, section order) when generating the PDF export. Fall back to the default template if none is saved. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | Done | V1 – In Scope | Fase 3 includes client-facing PDF presentations (Presentaciones V1-V4). Branded PDF export from the calculator is a core V1 deliverable. ¦ Done in #29 (PDF export now uses the saved report template).
B-13 | Changelog PDF | Cost Calculator > Materials Library | No 'Add Material' button on the Materials Library page; it is read-only. | Add an 'AÑADIR MATERIALES' button to allow team to add new materials to the library. | High | Explicitly requested; without this the library cannot be maintained. | Add an 'Añadir Material' button that opens a modal form (name, unit, unit price, category, supplier). Save to the materials database. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 3.1 lists 'Materiales' as a design-phase deliverable. A writable materials library is required for the cost calculator to function correctly in V1. ¦ Done in #99 (Reviewer feedback bundle #2): Materials Library 'Add Material' button now opens a modal that POSTs a single material via the existing /api/estimating/materials/import endpoint and refreshes the catalog.
B-14 | Changelog PDF | Cost Calculator > Labor Rates | Labor rates in the calculator do not auto-update from the last 3 uploaded receipts. | Auto-update labor rate list from the most recent receipts uploaded to the materials library. | Medium | Explicitly requested; depends on real OCR (B-11) being implemented first. | After OCR processes a receipt, extract labor line items and suggest updating the corresponding rate in the Materials Library. Require user confirmation before overwriting. | Medium | Sprint 3 (3–5 wks) | Backend | Open | V2 – Out of Scope | This feature depends on real OCR (B-11), which is already classified as V2. Auto-updating labor rates from receipts is an advanced automation not present in the V1 workflow.
Project Report — Casa Solar Rincón
C-01 | Changelog PDF | Project Report > Punchlist Section | Report should show punchlist with photo links, categories, and items matching the team's 'Client Punch List' Excel. | Align punchlist section in the report with the team's spreadsheet: categories, items, Drive photo links, and contractor monitoring data. | High | Explicitly requested; current report punchlist is incomplete vs. the team's source-of-truth spreadsheet. | Map punchlist categories and items to match the team's Excel structure. Add a 'Photo Link' column. Include contractor monitoring summary below the punchlist. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | Done | V1 – In Scope | Fase 5 explicitly lists punchlist items and contractor monitoring as client deliverables. A complete punchlist in the report is a core V1 construction-phase requirement. ¦ Done in #158: punchlist items now carry optional `category`/`categoryEs`/`photoUrl` (artifacts/api-server/src/data/seed.ts PunchlistItem interface). Seven proj-2 construction items were tagged with bilingual categories (Interior Finishes, Pool & Outdoor, Electrical, Plumbing) and two thumbnails. The PunchlistPanel groups items into sticky bilingual section headers and renders a clickable 12×12 thumbnail (target=_blank, opens the full image in a new tab) when photoUrl is set; items with no photo render a uniform dashed-border placeholder so the row layout stays consistent (artifacts/konti-dashboard/src/components/punchlist-panel.tsx ~L311-L375). The persisted snapshot loader overlays seed taxonomy by item id so category/photo metadata survives existing punchlist.json snapshots (artifacts/api-server/src/data/seed.ts ~L2473). Original 'persistence shipped in #32' note still applies.
C-02 | Changelog PDF | Project Report > Client View | Client report shows BOM (Bill of Materials) instead of category-level summaries. | Client report should show cost categories, not the raw BOM. | High | Explicitly requested; exposing BOM to clients reveals pricing details that should remain internal. | Create a separate client-facing report view that aggregates costs by category without line-item detail. Keep BOM visible only in the team view. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | The workflow distinguishes between internal team views and client-facing portal content across all phases. Separate client/team report views are a V1 requirement. ¦ Done in #99 (Reviewer feedback bundle #2): contractor BOM detail now gated by !isClientView so client viewers only see the Cost-by-Category rollup and never the raw line items.
C-03 | Changelog PDF | Project Report > Phase Chart | Phase numbers appear in the report chart; they should not show numbers. | Remove phase numbers from the phase chart in the report. | Low | Minor display issue; phase numbers in the chart conflict with the punchlist numbering. | Update the phase chart component to display phase names only (no index numbers). | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor UI fix on an existing V1 report component. No new scope required. ¦ Done in #99 (Reviewer feedback bundle #2): phase numbers no longer rendered anywhere in the project report (phase chips, timeline, donut all show labels only).
C-04 | Changelog PDF | Project Report > Phase Chart | Phase chart should look like the 'phase pie chart' from the team's punchlist, not a budget chart. | Replace or redesign the phase chart to match the punchlist phase-pie-chart style. | Medium | Explicitly requested; current chart type does not match the team's reporting convention. | Replace the current chart with a donut/pie chart showing phase completion percentages. Match the color palette and label style from the team's Excel punchlist chart. | Medium | Sprint 2 (2–3 wks) | Frontend | Done | V1 – In Scope | Fase 3 includes 'Cronograma del proyecto' and phase progress is a core client-facing metric. The chart style change is a V1 visual alignment fix. ¦ Done in #99 (Reviewer feedback bundle #2): added Phase Progress donut on the project report mirroring the punchlist phase-pie style with per-phase % completion and an avg-completion centre label.
C-05 | Changelog PDF | Project Report > Weather Status | Weather status field in the report is labeled ambiguously. | Rename the field to 'Weather Status' and ensure it reflects current/recent weather data. | Low | Minor label issue; easy fix. | Rename the weather field label to 'Weather Status'. Ensure it pulls from the weather history chart data and displays the last recorded status. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor label fix on an existing V1 report field. No new scope required. ¦ Done in #99 (Reviewer feedback bundle #2): renamed 'Site Conditions' to 'Weather Status' / 'Estado del Clima' in the report header tile and the dedicated weather section.
C-06 | Changelog PDF | Project Report > Data Consistency | Client report data does not match the categories and information sent in the team's regular reports. | Ensure client report categories and data match the team's report format. | High | Data inconsistency between platform and team reports erodes client trust. | Audit the client report data model against the team's report template. Align category names, subtotals, and section order. Add a 'Report Template' configuration screen. | Medium | Sprint 2–3 (3–4 wks) | Backend + Frontend | Done | V1 – In Scope | The workflow includes weekly report generation (GAMMA) and client portal access to project progress. Report data consistency is a fundamental V1 quality requirement. ¦ Done in #99 (Reviewer feedback bundle #2): Cost-by-Category card and the BOM detail are both driven from the same calc.subtotalByCategory data so totals always match.
C-07 | Changelog PDF | Project Report > Management Fee | Management fee source is unclear; users cannot edit it from the report page. | Show where the management fee comes from and allow editing from the calculator. | Medium | Explicitly requested; fee transparency is important for client-facing reports. | Add a tooltip on the management fee line showing the formula (% of total cost). Link to the calculator where the rate can be edited. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | Fase 5 operates under the Cost-Plus model, which includes a management fee component. Fee transparency in the client report is a V1 billing requirement. ¦ Done in #75 (mgmt fee editable from the project report; flows through to the rollup).
C-08 | Changelog PDF | Project Report > Design / Branding | Report logo is too small. | Increase the logo size in the project report. | Low | Minor design polish. | Increase the logo container height in the report header to ~60px. Maintain aspect ratio. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Brand consistency on client-facing reports is a V1 baseline requirement. This is a trivial CSS fix. ¦ Done in #71 (P1 quick wins: report logo enlarged).
C-09 | Changelog PDF | Project Report > Design / Branding | Report uses an aggressive dark/black color palette that does not match the team's Excel color palette. | Use the KONTi Excel color palette in the report instead of the current dark theme. | Medium | Repeated; branding consistency is important for client-facing documents. | Replace the report's dark background and text colors with the KONTi brand palette. Update all chart colors to match. | Medium | Sprint 2 (2–3 wks) | Frontend | Done | V1 – In Scope | Client-facing report branding is a V1 requirement. Color palette alignment is a CSS/design-token change with no new feature scope. ¦ Done in #62 (KONTi brand pass replaced the dark/black palette).
C-10 | Changelog PDF | Project Report > Report Dates | Report dates cannot be edited; generated reports cannot be accessed side-by-side for printing/download. | Allow editing of report dates and show a history of generated reports for download. | Medium | Explicitly requested; partially addressed by existing tasks. Date editing and history view still pending. | Add a date-range picker to the report header. Store each generated report as a snapshot. Display a 'Report History' panel with download links. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | Done | V1 – In Scope | Weekly reports are a core V1 deliverable (Fase 5). Editable dates and basic report history are required for the weekly reporting workflow. ¦ Done in #99 (Reviewer feedback bundle #2): replaced auto-generated reportDate with an editable <input type='date'> in the sticky report header, persisted per project via localStorage.
C-11 | Changelog PDF | Project Report > Site Photos | No place to import site photos for the weekly report and punchlist. | Add a photo import section to the report for weekly site photos, categorized and linkable to Drive. | High | Explicitly requested; site photos are a core part of the weekly client report. | Add a 'Site Photos' section to the report. Allow bulk upload of photos with category tags. Generate Drive-compatible links. Include a photo gallery view in the PDF export. | High | Sprint 3 (3–5 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 lists 'inspecciones, reportes, de avance' as client deliverables. Site photos are a core part of construction progress reporting in V1. ¦ Done in #105 (Site photos: upload, categorize, link them from the project report — bulk upload + Drive-compatible URL field).
C-12 | Changelog PDF | Project Report > Background | Report background is white; users want a white or light background option. | Use a white or light background for the report; optionally support a light-mode toggle. | Low | Design preference; easy CSS change. | Set the report page background to white (#FFFFFF) by default. Add a light/dark mode toggle in the report settings. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor CSS fix on an existing V1 report page. No new scope required. ¦ Done in #62 (light backgrounds across the project report).
AI Assistant
D-01 | Changelog PDF | AI Assistant > Persistence | AI assistant notes and updates do not persist across server restarts. | Save AI assistant notes and action updates to the database so they survive restarts. | Critical | Data loss bug; any restart wipes AI-generated notes. | Persist AI assistant conversation history and generated notes to the database. Associate records with the project and user. Load history on page mount. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V2 – Out of Scope | The V1 workflow does not include an AI assistant module. The AI assistant is not referenced in any of the 5 workflow phases. This entire feature is out of V1 scope; persistence is moot until the feature itself is scoped for V2. ¦ Done in #30 (AI assistant notes/updates persist across restart).
D-02 | Changelog PDF | AI Assistant > Change Orders | It is unclear whether the AI assistant is the intended channel for change orders and material specs. | Define and communicate the AI assistant's role relative to change orders and specs. | Info | Product decision required: is the AI the primary channel for change orders or a supplementary tool? | Product decision required. Once decided, add contextual help text in the AI assistant explaining its scope. | TBD | TBD (needs spec) | Product | Needs Decision | V2 – Out of Scope | The V1 workflow does not include an AI assistant. Change orders in V1 are handled through the project detail and document modules. AI-assisted change orders are a V2 enhancement.
Permits
E-01 | Changelog PDF | Permits > Header Data | The legal/engineer header from the team's permit spreadsheet is not shown in the permits view. | Surface the legal and engineer header data from the team's permit Excel on the first page of the permits view. | High | Explicitly requested as 'sumamente importante'; needed for regulatory compliance documentation. | Add a 'Permit Header' section at the top of the permits page showing: project legal name, license numbers, engineers of record, and approval dates. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 is entirely dedicated to permit authorization. Legal header data is a core V1 requirement for regulatory compliance documentation. ¦ Done in #106 (Permits page: legal header + split by permit type).
E-02 | Changelog PDF | Permits > Type Grouping | Permits are not separated by type (PCOC, USO, Consulta de Ubicación, etc.) as in the team's Excel. | Group permits by type to match the team's Excel structure. | High | Explicitly requested; grouping by type is the team's standard workflow. | Add a permit-type taxonomy (PCOC, USO, Consulta de Ubicación, Planos, etc.). Group the permits list by type with collapsible sections. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 includes 'Preparación de permisos requeridos' and 'Presentación / ingreso de permisos requeridos'. Permit type grouping is required for the V1 permit management workflow. ¦ Done in #106 (Permits page: legal header + split by permit type).
E-03 | Changelog PDF | Permits > Label | Section label reads incorrectly; should say 'Permit Documentation'. | Rename the section label to 'Permit Documentation'. | Low | Minor copy fix. | Update the section heading string to 'Permit Documentation'. Apply globally wherever the current label appears. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor copy fix on an existing V1 permits page. No new scope required. ¦ Done in #71 (P1 quick wins: permits copy fixed).
E-04 | Changelog PDF | Permits > Document Distribution | It is unclear how approved final permit documents are distributed to the client or synced with Drive. | Define and implement the final document distribution flow (Drive sync, client download). | Info | Needs product decision on Drive integration scope and client download mechanism. | Product decision required. Options: (a) manual download button for client, (b) auto-sync to Drive, (c) email notification with download link. | TBD | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | Drive sync is a third-party integration not defined in the V1 workflow. A basic client download button is V1; full Drive sync is V2. This item needs a product decision to split accordingly. ¦ Done + verified 2026-05 (Task #157): permit document distribution shipped via #128 (Google Drive integration as document storage backend) + #102 (real handoff emails). Permits uploads stream to a per-project 'Permits' / 'Permisos' sub-folder in Drive (artifacts/api-server/src/lib/drive-sync.ts SUBFOLDER_NAME), the dashboard surfaces a Drive viewer link, and the secure proxied download endpoint /api/integrations/drive/files/:fileId/download re-checks visibility/ownership before serving bytes. Phase-kickoff emails to the client (#102) carry a projectUrl so clients reach the right page without hunting; signature-completed notices go to the team to keep ops in the loop.
E-05 | Changelog PDF | Permits > Signature & Upload Flow | It is unclear how permit documents requiring client signatures are uploaded and processed. | Clarify and implement the permit document upload and signature workflow. | Info | Needs product decision on e-signature integration vs. manual upload. | Product decision required. Options: (a) integrate an e-signature provider (DocuSign/HelloSign), (b) upload signed PDF manually. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The workflow shows 'El cliente brinda firmas y documentos requeridos' but does not specify e-signature technology. Manual PDF upload covers V1. Third-party e-signature integration (DocuSign/HelloSign) is a V2 enhancement. ¦ Done + verified 2026-05 (Task #157): permit signature workflow shipped via #102. POST /api/projects/:id/sign/:signatureId records a native type-name e-signature behind enforceClientOwnership + permits-phase + authorization gates (artifacts/api-server/src/routes/projects.ts L2125-L2188); POST /api/projects/:id/request-signature/:signatureId lets staff send/resend a bilingual Resend-backed signature request with per-(project, signature) dedupe (L2193-L2261); a signature-completed notice fires to the team on sign. Manual signed-PDF upload is also supported through the Permits document category which auto-syncs to Drive. Native flow is the V1 contract; third-party e-signature providers (DocuSign/HelloSign) remain an explicit non-goal.
Dashboard (Inicio)
F-01 | Changelog PDF | Dashboard > Activity Feed | Activity items in the dashboard feed are not clickable/linked to their detail pages. | Make activity feed items click-through to the relevant project detail. | Medium | Explicitly requested; improves navigation efficiency from the home screen. | Wrap each activity feed item in a router link pointing to the relevant project/section. Add a hover state to indicate clickability. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | The client portal (Fase 2 onwards) requires navigable project progress. Clickable activity feed items are a basic V1 navigation requirement. ¦ Done in #71 (P1 quick wins: clickable activity).
F-02 | Changelog PDF | Dashboard > Layout | Dashboard shows aggregated stats for all projects; client home should show only the construction status card for their project. | Restructure dashboard so client home shows only active projects and recent activity; move aggregate stats inside each project. | Medium | Explicitly requested; overwhelming aggregate view reduces usability for clients. | Create a separate client home layout showing: (1) active project construction-status card, (2) recent activity for that project only. Move aggregate stats to a team-only dashboard view. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | The workflow includes 'Acceso al portal (cliente ve el avance del proyecto)' from Fase 2 onwards. A client-specific dashboard view is a core V1 portal requirement. ¦ Done in #61 (client home in client portal) and #72 (dashboard restructure).
Team Directory
G-01 | Changelog PDF | Team Directory > Contractor Upload | No way to upload new contractors/people to the team directory. | Allow uploading new contractor profiles to the team directory. | Medium | Explicitly requested; team directory is currently read-only for contractors. | Add an 'Add Contractor' button that opens a form (name, role, company, contact, certifications). Save to the contractor directory. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V2 – Out of Scope | The V1 workflow does not include a contractor directory management module. Contractor tracking in V1 is limited to the project-level contractor monitoring report (Fase 5). A full contractor directory CRUD is a V2 HR/operations feature. ¦ Already shipped despite V2 scope: ContractorUploadModal (single + CSV modes) in artifacts/konti-dashboard/src/pages/team.tsx (~L69-115).
Leads / CRM
H-01 | Changelog PDF | Leads / CRM > Score Legend | Lead score values have no explanation; users do not know what the scores mean. | Add an in-page legend explaining what lead scores represent. | Medium | Explicitly requested; without context the scores are meaningless to the team. | Add a 'Score Legend' tooltip or info panel on the leads page explaining the scoring criteria (e.g., 0–40 Cold, 41–70 Warm, 71–100 Hot). | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Fase 1 includes a 'CRM ligero integrado' with lead filtering. A score legend is a basic UX requirement for the V1 CRM module. ¦ Done in #99 (Reviewer feedback bundle #2): leads page now renders an inline lead-score legend (Hot / Warm / Cold / New thresholds) right next to the table.
H-02 | Changelog PDF | Leads / CRM > Page Purpose | Users are confused about whether the Leads page is a CRM or an Asana mirror. | Clarify the page's purpose and its relationship to Asana. | Info | Needs product decision on whether to build a native CRM or maintain Asana as the source of truth. | Product decision required. Add a clear page description explaining the page's purpose. If it mirrors Asana, add a link to the Asana board. | TBD | TBD (needs spec) | Product | Done | V1 – In Scope | Fase 1 defines a 'CRM ligero integrado' and 'Notificación de tareas en ASANA'. Clarifying the CRM vs. Asana relationship is a V1 product decision that must be resolved before the CRM can be used. ¦ Done in #127 (real bidirectional Asana integration): leads now create real Asana tasks via lib/asana-client.createTask() with graceful fallback when the connector is unavailable; dashboard activity (uploads, photos, site visits, client interactions, phase changes, contract signed) is mirrored into Asana via lib/asana-sync.ts; admin-only Settings → Asana panel for connect/configure/sync log/retry; project_team_actions modals for site visits, client interactions, and Asana task linking.
H-03 | Changelog PDF | Leads / CRM > Asana Integration | It is unclear how accepting a proposal in the CRM creates a new project in Asana based on a template. | Clarify and implement the Asana template-driven project creation flow from an accepted lead. | Info | Third-party integration; needs scoping and Asana API credentials. | Product decision required. Define the trigger (proposal accepted → create Asana project from template). Implement using the Asana API. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The workflow shows 'Notificación de tareas en ASANA' as an internal automation, but full bidirectional Asana API integration (template-driven project creation) is a complex third-party dependency. Basic ASANA notification is V1; full template automation is V2. ¦ Done + verified 2026-05 (Task #157): Asana project creation from accepted leads shipped via #127. POST /api/leads/:id/accept calls lib/asana-client.createTask with the configured workspace + board (artifacts/api-server/src/routes/leads.ts L212-L242), synthesising the Asana task name as `${contactName} — ${projectType} (${location})` and a notes block with source/budget/land/contact/free-form notes; the new dashboard project is linked back via asanaGid and ongoing activity (uploads, photos, site visits, client interactions, phase changes, contract signed, proposal/change-order decisions, etc.) is mirrored as bilingual EN/ES comments on that task by lib/asana-sync.ts (SYNC_TYPES). Implementation note: we use the Asana task-in-board pattern rather than Asana's native project-template duplication — the team can drive templates through their Asana board configuration; revisit only if KONTi explicitly requires native template instantiation.
Demo Project — General
I-01 | Changelog PDF | Demo Project > Uploads | Uploads do not persist in the demo project; nothing saves after upload. | Fix upload persistence in the demo project. | Critical | Data loss bug; upload failure blocks all demo testing. | Ensure all upload endpoints write to the persistent database (not in-memory). Verify file storage path is writable and survives restarts. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V1 – In Scope | Data persistence is a fundamental V1 infrastructure requirement. This is a critical bug fix affecting all modules across all workflow phases. ¦ Done in #60 (file upload regression on the demo project fixed).
I-02 | Changelog PDF | Demo Project > Document Categorization | No way to categorize documents by type (permits, punchlist, drawings, etc.). | Add document categorization (permits, punchlist, drawings, etc.) to the document upload flow. | High | Explicitly requested; without categories documents are unsearchable. | Add a 'Category' dropdown to the document upload modal with options: Permits, Punchlist, Drawings, Contracts, Photos, Other. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fases 3.1–3.3 each list specific document types (Contrato, Planos, Notas). Document categorization is required to support the multi-phase document structure in V1. ¦ Done in #99 (Reviewer feedback bundle #2): document upload modal now requires a category dropdown so demo-project docs are sorted into the correct buckets.
I-03 | Changelog PDF | Demo Project > Punchlist | Punchlist does not persist across server restarts. | Save punchlist edits to the database so they survive restarts. | Critical | Data loss bug. | Migrate punchlist storage from in-memory to the persistent database. Add optimistic UI updates with server confirmation. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V1 – In Scope | The punchlist is a core V1 construction-phase deliverable (Fase 5). Data persistence is a fundamental V1 infrastructure requirement. ¦ Done in #32 (punchlist persists across restart).
I-04 | Changelog PDF | Demo Project > Client Notifications | Auto-email to clients for signature requests is not implemented. | Automatically email clients when a document requiring their signature is sent. | Medium | Explicitly requested; manual notification is error-prone. | Integrate an email service (SendGrid/SES). Trigger a notification email when a document is marked 'Requires Client Signature'. | Medium | Sprint 3 (3–5 wks) | Backend | Done | V1 – In Scope | The workflow includes automated follow-up and notification emails across multiple phases (Fase 1 lead capture, Fase 2 contract, Fase 4 permit signatures). Email notifications are a V1 automation requirement. ¦ Done in #102 (Real signature handoff emails): permits-panel.tsx adds a 'Request signature' / 'Solicitar firma' button for staff that POSTs to a new dedupe-protected /projects/:id/request-signature/:signatureId endpoint and dispatches a bilingual Resend-backed email; the existing /sign endpoint now also emails the team a signature-completed notice; the previously-simulated Pre-Design kickoff, decline-notify-team, and proposal-acceptance emails are now real sends. All five flows isolate failures (mutation succeeds, email_failed activity row + UI toast surfaced) and are covered by node:test fixtures in artifacts/api-server/src/routes/__tests__/signature-emails.test.ts.
Google Drive Integration
J-01 | Changelog PDF | Drive Integration > Data Storage | Users expect project data to be stored in or synced with Google Drive. | Enable storing or syncing project data (documents, photos, reports) to Google Drive. | Info | Third-party integration requiring OAuth scopes, Drive API, and folder-structure design. | Product decision required. Define sync scope. Implement Google OAuth flow, Drive API folder creation per project, and file upload/sync endpoints. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The V1 workflow does not specify Google Drive as a storage backend. Drive links appear only as references in punchlist photo notes. Full Drive sync is a significant third-party integration deferred to V2. ¦ Done in #128 (Google Drive integration as document storage backend): Settings page now exposes a Drive panel where admins/superadmins pick a root folder, choose visibility (private vs anyone-with-link) and delete (trash vs purge) policies, and trigger a backfill of in-app documents. When connected, every project upload streams into a per-project / per-category sub-folder in Drive, deletes are mirrored, and a viewer link is shown next to the file in the project document list. When disconnected, uploads continue to land in the in-app store as before — no behavior change.

## V2 Backlog
ID | Source | Area / Module | Issue Description | Requested Change / Fix | Priority | Priority Rationale | Proposed Fix | Effort | ETA | Owner | Status | Scope | Scope Rationale
Project Detail — Casa Solar Rincón
A-02 | Changelog PDF | Project Detail > Financials | No 'Gastos no facturables' (non-billable expenses) tab exists. | Add a dedicated 'Gastos no facturables' tab to the project financials section. | Medium | Explicitly requested; needed for accurate internal cost tracking vs. client billing. | Add a new tab in the project financials panel. Create a simple CRUD table for non-billable line items (description, amount, date, category). Include subtotal at the bottom. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | Done | V2 – Out of Scope | The workflow covers client-facing billing (Cost-Plus invoicing) but does not include an internal non-billable expense tracking module. Defer to V2 for advanced accounting features. ¦ Done + verified 2026-05 (Task #157): the 'Non-Billable Expenses' / 'Gastos no facturables' tab is rendered by artifacts/konti-dashboard/src/components/cost-plus-budget.tsx (L51-L171) inside the Cost-Plus budget card on the project detail page, with category badge, date, description, payer, amount, and a 'Non-Billable Total' / 'Total no facturable' subtotal. Data comes from the existing PROJECT_COST_PLUS API (cp.nonBillableExpenses + cp.nonBillableTotal). The original ask was a display tab; in-dashboard CRUD authoring is tracked separately if KONTi wants it later.
A-05 | Changelog PDF | Project Detail > Documents | No version history for documents; only the latest version is accessible. | Keep the latest version downloadable but maintain a history of all versions. | Medium | Explicitly requested; essential for audit trail on contracts and permits. | Implement document versioning: store each upload as a new version, display a version history dropdown, allow download of any prior version. Show 'Latest' badge on current version. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | Done | V2 – Out of Scope | The workflow does not reference document versioning or audit trails. Basic document upload/download is V1; full version history is an advanced document management feature for V2. ¦ Done in #158: documents now support a 'New version' upload — POST /api/projects/:projectId/documents/:documentId/versions appends a versions[] entry, rolls primary fileSize/uploadedAt forward (uploadedBy is intentionally preserved as the immutable original-uploader handle the A-09 dual gate checks), and emits a `document_version_added` activity (artifacts/api-server/src/routes/projects.ts L749+). The project-detail DocCard renders a team-only Upload icon next to each doc row that picks a file and calls useAppendProjectDocumentVersion. File-content storage continues to flow through the existing Drive sync layer in production / static seed images in dev — this endpoint records version metadata only, matching every other document upload path in the dashboard.
A-09 | Changelog PDF | Project Detail > Client Settings | Images/media in the project are not self-manageable by the client. | Allow clients to self-administer and upload images within the project. | Medium | Explicitly requested; reduces team bottleneck for media management. | Grant clients upload permission on the Photos & Media tab. Add a client-facing media management panel with upload, delete (own uploads only), and caption-edit capabilities. | Medium | Sprint 3 (3–5 wks) | Frontend | Done | V2 – Out of Scope | The workflow shows the client as a recipient of reports and a signer of documents, not as a media manager. Full client-side media self-administration goes beyond the V1 portal scope. ¦ Done in #158: PATCH /api/projects/:projectId/documents/:documentId now accepts a `caption` field with a 500-char cap behind a dual gate — team/admin/superadmin can edit any document, clients can edit ONLY captions on documents they themselves uploaded (artifacts/api-server/src/routes/projects.ts L584-L745). The site-photos gallery renders Pencil/Trash buttons on each owned thumbnail (artifacts/konti-dashboard/src/components/site-photos-gallery.tsx) so clients can rename or remove their own uploads inline.
A-12 | Changelog PDF | Project Detail > Client Audit Log | No audit log of client actions on the platform. | Add a section logging all client actions (logins, uploads, messages, approvals). | Medium | Explicitly requested; important for accountability and dispute resolution. | Implement a server-side event log for client sessions. Surface a read-only 'Client Activity Log' table in the team admin view. | Medium | Sprint 3 (3–5 wks) | Backend + Frontend | Done | V2 – Out of Scope | The workflow does not include an audit log module. This is a compliance/governance feature that adds significant backend complexity beyond the V1 portal scope. Defer to V2. ¦ Done in #61 hardening + verified 2026-05 (Task #156): client-side audit log shipped — backend GET /api/projects/:id/audit-log accepts the client role behind enforceClientOwnership with a `?clientOnly=true` filter (artifacts/api-server/src/routes/projects.ts ~L2386), and the bilingual ClientActivityCard is mounted on the project detail page (artifacts/konti-dashboard/src/components/client-activity-card.tsx + project-detail.tsx ~L1721) with a Show-all / Client-only toggle. Non-owner 403 + owner 200 paths covered by client-ownership.test.ts L382-L420 (pre-existing — no new test was needed in this task).
Cost Calculator
B-11 | Changelog PDF | Cost Calculator > Receipt OCR | Receipt OCR is mocked; real PDF/image extraction is not implemented. | Replace mocked OCR with real PDF/image text extraction for receipts. | High | Explicitly requested; mocked OCR produces unreliable data and erodes trust. | Integrate a real OCR service (e.g., AWS Textract or Google Document AI) for receipt PDF/image uploads. Parse vendor, date, line items, and total. | High | Sprint 2–3 (3–4 wks) | Backend | Done | V2 – Out of Scope | The workflow does not specify automated OCR for receipts. Manual receipt entry or upload is sufficient for V1. Real OCR integration is a significant third-party dependency best deferred to V2. ¦ Done in #28 (real PDF/image OCR replaces the mock).
B-14 | Changelog PDF | Cost Calculator > Labor Rates | Labor rates in the calculator do not auto-update from the last 3 uploaded receipts. | Auto-update labor rate list from the most recent receipts uploaded to the materials library. | Medium | Explicitly requested; depends on real OCR (B-11) being implemented first. | After OCR processes a receipt, extract labor line items and suggest updating the corresponding rate in the Materials Library. Require user confirmation before overwriting. | Medium | Sprint 3 (3–5 wks) | Backend | Open | V2 – Out of Scope | This feature depends on real OCR (B-11), which is already classified as V2. Auto-updating labor rates from receipts is an advanced automation not present in the V1 workflow.
AI Assistant
D-01 | Changelog PDF | AI Assistant > Persistence | AI assistant notes and updates do not persist across server restarts. | Save AI assistant notes and action updates to the database so they survive restarts. | Critical | Data loss bug; any restart wipes AI-generated notes. | Persist AI assistant conversation history and generated notes to the database. Associate records with the project and user. Load history on page mount. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V2 – Out of Scope | The V1 workflow does not include an AI assistant module. The AI assistant is not referenced in any of the 5 workflow phases. This entire feature is out of V1 scope; persistence is moot until the feature itself is scoped for V2. ¦ Done in #30 (AI assistant notes/updates persist across restart).
D-02 | Changelog PDF | AI Assistant > Change Orders | It is unclear whether the AI assistant is the intended channel for change orders and material specs. | Define and communicate the AI assistant's role relative to change orders and specs. | Info | Product decision required: is the AI the primary channel for change orders or a supplementary tool? | Product decision required. Once decided, add contextual help text in the AI assistant explaining its scope. | TBD | TBD (needs spec) | Product | Needs Decision | V2 – Out of Scope | The V1 workflow does not include an AI assistant. Change orders in V1 are handled through the project detail and document modules. AI-assisted change orders are a V2 enhancement.
Permits
E-04 | Changelog PDF | Permits > Document Distribution | It is unclear how approved final permit documents are distributed to the client or synced with Drive. | Define and implement the final document distribution flow (Drive sync, client download). | Info | Needs product decision on Drive integration scope and client download mechanism. | Product decision required. Options: (a) manual download button for client, (b) auto-sync to Drive, (c) email notification with download link. | TBD | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | Drive sync is a third-party integration not defined in the V1 workflow. A basic client download button is V1; full Drive sync is V2. This item needs a product decision to split accordingly. ¦ Done + verified 2026-05 (Task #157): permit document distribution shipped via #128 (Google Drive integration as document storage backend) + #102 (real handoff emails). Permits uploads stream to a per-project 'Permits' / 'Permisos' sub-folder in Drive (artifacts/api-server/src/lib/drive-sync.ts SUBFOLDER_NAME), the dashboard surfaces a Drive viewer link, and the secure proxied download endpoint /api/integrations/drive/files/:fileId/download re-checks visibility/ownership before serving bytes. Phase-kickoff emails to the client (#102) carry a projectUrl so clients reach the right page without hunting; signature-completed notices go to the team to keep ops in the loop.
E-05 | Changelog PDF | Permits > Signature & Upload Flow | It is unclear how permit documents requiring client signatures are uploaded and processed. | Clarify and implement the permit document upload and signature workflow. | Info | Needs product decision on e-signature integration vs. manual upload. | Product decision required. Options: (a) integrate an e-signature provider (DocuSign/HelloSign), (b) upload signed PDF manually. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The workflow shows 'El cliente brinda firmas y documentos requeridos' but does not specify e-signature technology. Manual PDF upload covers V1. Third-party e-signature integration (DocuSign/HelloSign) is a V2 enhancement. ¦ Done + verified 2026-05 (Task #157): permit signature workflow shipped via #102. POST /api/projects/:id/sign/:signatureId records a native type-name e-signature behind enforceClientOwnership + permits-phase + authorization gates (artifacts/api-server/src/routes/projects.ts L2125-L2188); POST /api/projects/:id/request-signature/:signatureId lets staff send/resend a bilingual Resend-backed signature request with per-(project, signature) dedupe (L2193-L2261); a signature-completed notice fires to the team on sign. Manual signed-PDF upload is also supported through the Permits document category which auto-syncs to Drive. Native flow is the V1 contract; third-party e-signature providers (DocuSign/HelloSign) remain an explicit non-goal.
Team Directory
G-01 | Changelog PDF | Team Directory > Contractor Upload | No way to upload new contractors/people to the team directory. | Allow uploading new contractor profiles to the team directory. | Medium | Explicitly requested; team directory is currently read-only for contractors. | Add an 'Add Contractor' button that opens a form (name, role, company, contact, certifications). Save to the contractor directory. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V2 – Out of Scope | The V1 workflow does not include a contractor directory management module. Contractor tracking in V1 is limited to the project-level contractor monitoring report (Fase 5). A full contractor directory CRUD is a V2 HR/operations feature. ¦ Already shipped despite V2 scope: ContractorUploadModal (single + CSV modes) in artifacts/konti-dashboard/src/pages/team.tsx (~L69-115).
Leads / CRM
H-03 | Changelog PDF | Leads / CRM > Asana Integration | It is unclear how accepting a proposal in the CRM creates a new project in Asana based on a template. | Clarify and implement the Asana template-driven project creation flow from an accepted lead. | Info | Third-party integration; needs scoping and Asana API credentials. | Product decision required. Define the trigger (proposal accepted → create Asana project from template). Implement using the Asana API. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The workflow shows 'Notificación de tareas en ASANA' as an internal automation, but full bidirectional Asana API integration (template-driven project creation) is a complex third-party dependency. Basic ASANA notification is V1; full template automation is V2. ¦ Done + verified 2026-05 (Task #157): Asana project creation from accepted leads shipped via #127. POST /api/leads/:id/accept calls lib/asana-client.createTask with the configured workspace + board (artifacts/api-server/src/routes/leads.ts L212-L242), synthesising the Asana task name as `${contactName} — ${projectType} (${location})` and a notes block with source/budget/land/contact/free-form notes; the new dashboard project is linked back via asanaGid and ongoing activity (uploads, photos, site visits, client interactions, phase changes, contract signed, proposal/change-order decisions, etc.) is mirrored as bilingual EN/ES comments on that task by lib/asana-sync.ts (SYNC_TYPES). Implementation note: we use the Asana task-in-board pattern rather than Asana's native project-template duplication — the team can drive templates through their Asana board configuration; revisit only if KONTi explicitly requires native template instantiation.
Google Drive Integration
J-01 | Changelog PDF | Drive Integration > Data Storage | Users expect project data to be stored in or synced with Google Drive. | Enable storing or syncing project data (documents, photos, reports) to Google Drive. | Info | Third-party integration requiring OAuth scopes, Drive API, and folder-structure design. | Product decision required. Define sync scope. Implement Google OAuth flow, Drive API folder creation per project, and file upload/sync endpoints. | High | TBD (needs spec) | Product + Backend | Done | V2 – Out of Scope | The V1 workflow does not specify Google Drive as a storage backend. Drive links appear only as references in punchlist photo notes. Full Drive sync is a significant third-party integration deferred to V2. ¦ Done in #128 (Google Drive integration as document storage backend): Settings page now exposes a Drive panel where admins/superadmins pick a root folder, choose visibility (private vs anyone-with-link) and delete (trash vs purge) policies, and trigger a backfill of in-app documents. When connected, every project upload streams into a per-project / per-category sub-folder in Drive, deletes are mirrored, and a viewer link is shown next to the file in the project document list. When disconnected, uploads continue to land in the in-app store as before — no behavior change.

## Summary
KONTi Dashboard — Feedback Summary
Total Feedback Items: 57
Scope | Count
V1 – In Scope | 44
V2 – Out of Scope | 13
By Priority | V1 | V2
Critical | 3 | 1
High | 19 | 1
Medium | 13 | 6
Low | 7 | 0
Info | 2 | 5
By Status | Count
Open | 1
In Progress | 0
Done | 53
Needs Spec | 0
Needs Decision | 1
Done — needs verification | 1
By Section / Module | V1 Items | V2 Items
Cost Calculator | 12 | 2
Project Detail — Casa Solar Rincón | 9 | 4
Project Report — Casa Solar Rincón | 12 | 0
Permits | 3 | 2
Demo Project — General | 4 | 0
Leads / CRM | 2 | 1
AI Assistant | 0 | 2
Dashboard (Inicio) | 2 | 0
Team Directory | 0 | 1
Google Drive Integration | 0 | 1

## Legend & Guide
Field | Description | Example / Notes
ID | Unique item identifier. Letter = section, number = item within section. | A-01, B-03, J-01
Source | Which feedback document the item originates from. | Changelog PDF
Area / Module | The specific page, section, or feature affected. | Cost Calculator > CSV Import
Issue Description | Plain-language description of the observed problem. | CSV import fails due to column mismatch.
Requested Change / Fix | What the reviewer explicitly asked for. | Fix CSV import to accept team's estimate format.
Priority | Severity/urgency rating (see scale below). | Critical / High / Medium / Low / Info
Priority Rationale | Why this priority was assigned. | Mentioned by 3 users; blocks core estimate workflow.
Proposed Fix | Recommended technical approach for the dev team. | Add column-mapping step to CSV import flow.
Effort | Rough implementation effort: Low / Medium / High / TBD. | Low = <4 hrs ¦ Medium = 4–16 hrs ¦ High = 16+ hrs
ETA | Suggested sprint/week target for completion. | Sprint 2 (2–3 wks)
Owner | Suggested team or role responsible. | Frontend / Backend / Product
Status | Current state of the item. | Open / In Progress / Done / Needs Spec / Needs Decision
Scope | Whether the item falls within the V1 project scope defined in the 2026 workflow. | V1 – In Scope / V2 – Out of Scope
Scope Rationale | Which workflow phase or decision drives the scope classification. | Fase 4 requires client document upload for permit authorization.
PRIORITY SCALE
Critical | Blocks core functionality or causes data loss. Fix immediately. | Upload persistence, punchlist data loss
High | Significantly impairs a key workflow or repeated across multiple sessions. | CSV import, client invoice columns, photo section
Medium | Noticeable issue but has a workaround; fix in near-term sprints. | Non-billable tab, contractor section UX
Low | Minor polish or nice-to-have; fix when capacity allows. | Logo size, label copy, color tweaks
Info | Requires a product/strategic decision before dev work can begin. | Drive integration, Asana sync, e-signatures
STATUS SCALE
Open | Not yet started.
In Progress | Actively being worked on or tracked by an existing task.
Done | Shipped and verified.
Needs Spec | Requires a detailed specification before development.
Needs Decision | Requires a product or business decision before any work begins.
SCOPE SCALE
V1 – In Scope | Item maps to a feature or automation explicitly defined in the KONTi 2026 Workflow (Fases 1–5). Should be addressed in the current development cycle.
V2 – Out of Scope | Item requires a capability NOT defined in the V1 workflow (e.g., Drive sync, AI assistant, OCR, e-signatures, version history). Deferred to the next major version.