## KONTi Dashboard Feedback
ID | Source | Area / Module | Issue Description | Requested Change / Fix | Priority | Priority Rationale | Proposed Fix | Effort | ETA | Owner | Status | Scope | Scope Rationale | Verification Note (2026-04-30)
Project Detail — Casa Solar Rincón
A-01 | Changelog PDF | Project Detail > Financials | No per-invoice columns for client view (total amount, paid, balance, invoice status). | Add columns: Monto Total, Pagado, Saldo Pendiente, Estado per invoice on the client-facing financial tab. | High | Requested explicitly; clients need billing transparency without contacting the team. | Extend the client-view financial table with four new columns pulled from the existing invoice data model. Add color-coded status badge (Pagada / Pendiente / Vencida). | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 explicitly shows 'Estado de facturas / saldo pendiente' and Cost-Plus model tracking as part of the construction phase dashboard. | Verified at artifacts/konti-dashboard/src/components/project-invoices.tsx (Total/Paid/Balance/Status columns + bilingual status badge).
A-02 | Changelog PDF | Project Detail > Financials | No 'Gastos no facturables' (non-billable expenses) tab exists. | Add a dedicated 'Gastos no facturables' tab to the project financials section. | Medium | Explicitly requested; needed for accurate internal cost tracking vs. client billing. | Add a new tab in the project financials panel. Create a simple CRUD table for non-billable line items (description, amount, date, category). Include subtotal at the bottom. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | Open | V2 – Out of Scope | The workflow covers client-facing billing (Cost-Plus invoicing) but does not include an internal non-billable expense tracking module. Defer to V2 for advanced accounting features. | Confirmed: no Gastos no facturables tab in project-detail.tsx.
A-03 | Changelog PDF | Project Detail > Documents | Client cannot upload files; it is unclear whether they can and in which section. | Enable client-side document upload or clearly define the upload policy and location. | High | Repeated across multiple sessions; missing client upload capability blocks collaboration. | Add an 'Upload Document' button to the client view of the Documents tab. Restrict to PDF/image formats. Store in the project's document store with a 'Client Upload' tag visible to the team. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 requires 'El cliente brinda firmas y documentos requeridos' — client document upload is a core V1 requirement for permit authorization. | Client UploadModal in artifacts/konti-dashboard/src/pages/project-detail.tsx (~L138-320) with category picker.
A-04 | Changelog PDF | Project Detail > Documents | Documents are flat; no 'Contratos y Acuerdos de compra' grouping exists. | Organize the 'Acuerdos' category into a 'Contratos y Acuerdos de compra' sub-group. | Medium | Explicitly requested; improves document discoverability for legal/procurement docs. | Add a document-category taxonomy. Create a 'Contratos y Acuerdos de compra' category in the document type selector. Migrate existing Acuerdos documents to the new category. | Low | Sprint 1–2 (1–2 wks) | Frontend + Backend | Done | V1 – In Scope | Fases 3.1–3.3 list Contrato and Documentos as explicit deliverables per phase. Document categorization is required to support this multi-phase document structure. | DOC_CATEGORY_OPTIONS in project-detail.tsx (~L96) includes 'contratos' and 'acuerdos_compra'.
A-05 | Changelog PDF | Project Detail > Documents | No version history for documents; only the latest version is accessible. | Keep the latest version downloadable but maintain a history of all versions. | Medium | Explicitly requested; essential for audit trail on contracts and permits. | Implement document versioning: store each upload as a new version, display a version history dropdown, allow download of any prior version. Show 'Latest' badge on current version. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | Open | V2 – Out of Scope | The workflow does not reference document versioning or audit trails. Basic document upload/download is V1; full version history is an advanced document management feature for V2. | Confirmed: no document version history (V2).
A-06 | Changelog PDF | Project Detail > Documents | Team cannot control which documents are visible to the client. | Allow team to mark documents as 'Private' (team-only) vs. visible to client. | High | Repeated; team needs to share selectively — internal docs must never reach the client by default. | Add a 'Visibility' toggle (Private / Client) on each document row. Default new uploads to Private. Filter client document view to show only Client-visible documents. | Low | Sprint 1–2 (1–2 wks) | Frontend + Backend | Done | V1 – In Scope | The workflow distinguishes between internal team documents and client-facing deliverables across all phases. Document visibility control is a core V1 requirement. | isClientVisible flag on every document (seed.ts L436+); per-row toggle UI in project-detail.tsx (~L605-700).
A-07 | Changelog PDF | Project Detail > Photos & Media | No photos, video, or photo-comment section exists inside the project. | Add a Photos & Comments section where team and client can upload and annotate site photos. | High | Mentioned 4 times across different pages; core project communication feature. | Create a 'Fotos & Medios' tab in the project detail. Support image/video upload with caption and date. Allow threaded comments per photo. Link photos to punchlist items. | High | Sprint 3 (3–5 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 explicitly lists 'inspecciones, reportes, de avance y seguimiento de contratistas' delivered to the client. Site photos are a core part of construction progress reporting. | EN: Done in #105 — Photos & Media tab now lives on the project detail with bulk site-photo upload, category tags, and a per-project gallery rendered into the project report. File: artifacts/konti-dashboard/src/components/site-photos-gallery.tsx + artifacts/konti-dashboard/src/pages/project-detail.tsx. ¦ ES: Hecho en #105 — la pestaña Fotos & Medios ya existe en el detalle del proyecto con carga masiva de fotos de obra, etiquetas por categoría y una galería por proyecto incluida en el reporte. Archivo: artifacts/konti-dashboard/src/components/site-photos-gallery.tsx + artifacts/konti-dashboard/src/pages/project-detail.tsx.
A-08 | Changelog PDF | Project Detail > Client Settings | Client profile settings lack phone number, postal address, and physical address fields. | Add phone, dirección postal, and dirección física to the client configuration section. | Medium | Explicitly requested; needed for client communications and permit filings. | Add three new fields to the client settings form: Teléfono, Dirección Postal, Dirección Física. Persist to the client profile model. | Low | Sprint 1 (< 1 wk) | Frontend + Backend | Done | V1 – In Scope | Client profile data is required for permit documentation (Fase 4) and contract generation (Fases 2–3). Address and phone fields are basic CRM data captured in Fase 1. | phone, postalAddress, physicalAddress wired in artifacts/konti-dashboard/src/pages/settings.tsx (L15-46, L146-167).
A-09 | Changelog PDF | Project Detail > Client Settings | Images/media in the project are not self-manageable by the client. | Allow clients to self-administer and upload images within the project. | Medium | Explicitly requested; reduces team bottleneck for media management. | Grant clients upload permission on the Photos & Media tab. Add a client-facing media management panel with upload, delete (own uploads only), and caption-edit capabilities. | Medium | Sprint 3 (3–5 wks) | Frontend | Open | V2 – Out of Scope | The workflow shows the client as a recipient of reports and a signer of documents, not as a media manager. Full client-side media self-administration goes beyond the V1 portal scope. | Confirmed: clients cannot self-administer media (V2).
A-10 | Changelog PDF | Project Detail > Phases / Timeline | Parallel phases are not supported; the timeline assumes sequential phases only. | Clarify or implement support for phases running in parallel. | Info | Needs a product decision on whether to show a Gantt-style view or a parallel-phase indicator. | Product decision required: define parallel-phase UX (Gantt bars vs. split-phase cards). Once decided, implement phase-overlap data model and update the timeline visual. | High | TBD (needs spec) | Product + Frontend | Needs Decision | V1 – In Scope | The workflow header explicitly states 'las fases pueden ir en paralelo'. Parallel phase support is a V1 requirement. The Gantt visualization style is the open decision, not the parallel concept itself.
A-11 | Changelog PDF | Project Detail > Contractor Report | Contractor monitoring report lacks a consolidated view of delays, weather, issues, change orders, non-compliance, and rework. | Expand the contractor monitoring report to include all of the above data points. | High | Explicitly requested; partially addressed by existing tasks but a unified report view is still missing. | Consolidate weather data, change orders, punchlist items, and phase notes into a single 'Contractor Monitoring' report section. Add filters by date range and category. Export to PDF. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | In Progress | V1 – In Scope | Fase 5 explicitly lists 'seguimiento de contratistas, cumplimiento de contratos, incumplimientos' as deliverables to the client. Contractor monitoring is a core V1 construction-phase feature. | ContractorMonitoringSection renders status rows (components/contractor-monitoring-section.tsx L16-58) but seed has no separate delays/weather/issues/change-orders/non-compliance/rework fields. Unified report still missing.
A-12 | Changelog PDF | Project Detail > Client Audit Log | No audit log of client actions on the platform. | Add a section logging all client actions (logins, uploads, messages, approvals). | Medium | Explicitly requested; important for accountability and dispute resolution. | Implement a server-side event log for client sessions. Surface a read-only 'Client Activity Log' table in the team admin view. | Medium | Sprint 3 (3–5 wks) | Backend + Frontend | Open | V2 – Out of Scope | The workflow does not include an audit log module. This is a compliance/governance feature that adds significant backend complexity beyond the V1 portal scope. Defer to V2. | Confirmed: no client audit log surfaced (V2).
A-13 | Changelog PDF | Project Detail > Design / Branding | Dark gray color used in the project detail is too dark; does not match KONTi brand gray. | Replace the dark gray with the KONTi brand gray from the design guide. | Low | Design polish; mentioned alongside a Drive color reference. | Update the CSS design token for the primary gray (--color-gray-dark) to the KONTi brand value. Apply across all project-detail components. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Brand consistency is a baseline requirement for any client-facing V1 portal. This is a simple CSS token change with no scope implications. | KONTi gray (#778894) defined in artifacts/konti-dashboard/src/index.css (L75) and consumed via konti-slate token.
Cost Calculator
B-01 | Changelog PDF | Cost Calculator > CSV Import | Importing the team's initial estimate CSV fails because column format does not match the calculator's expected schema. | Fix CSV import so it accepts the team's existing estimate spreadsheet format. | High | Explicitly requested; blocks the primary data-entry workflow for estimates. | Add a CSV column-mapping step to the import flow: detect headers, let the user map source columns to calculator fields, then validate and import. Provide a downloadable template CSV. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 3 includes 'Herramientas de estimación de costos' and 'Envío de comparación real vs. estimado'. The cost calculator with CSV import is a core V1 estimation tool. | EN: CSV importer now uses smart EN/ES column mapping with override dropdowns, 5-row preview, skipped-row panel, and per-project mapping memory in localStorage (Task #112). Files: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx + e2e/csv-mapping-import.spec.ts. ¦ ES: El importador CSV ahora usa mapeo inteligente de columnas EN/ES con menús de sobrescritura, vista previa de 5 filas, panel de filas omitidas, y memoria de mapeo por proyecto en localStorage (Tarea #112). Archivos: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx + e2e/csv-mapping-import.spec.ts.
B-02 | Changelog PDF | Cost Calculator > Labor Model | Labor is calculated hourly, but the team works on lump-sum contracts. | Support lump-sum (suma alzada) labor entries in addition to hourly rates. | High | Core data-model mismatch; current hourly model creates confusion and incorrect totals. | Add a 'Labor Type' toggle per line item: Hourly (rate × hours) vs. Lump Sum (fixed amount). Update calculator totals and variance reports to handle both types. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | Open | V1 – In Scope | Fase 5 specifies 'Ejecución de obra bajo modelo Cost-Plus'. Accurate labor cost modeling (including lump-sum) is required for the Cost-Plus execution model in V1. | Confirmed: no Hourly vs Suma Alzada toggle in calculator/estimating.
B-03 | Changelog PDF | Cost Calculator > Materials | Materials do not auto-populate from the project; all materials must be entered manually. | Materials should auto-populate and be reflected automatically in the calculator. | High | Explicitly requested; manual re-entry is error-prone and time-consuming. | Link the Materials Library to the calculator: when a material is added to a project, auto-create a corresponding calculator line item. Allow manual override of quantity and unit price. | Medium | Sprint 2–3 (3–4 wks) | Backend + Frontend | In Progress | V1 – In Scope | Fase 3.1 lists 'Materiales' and 'Presupuesto' as explicit design-phase deliverables. Auto-populating materials in the cost calculator is required for accurate V1 estimates. | Calculator generates estimates from scratch (contractor-calculator.tsx L44-105); no link from project Materials Library yet.
B-04 | Changelog PDF | Cost Calculator > Base Price | Base price and quantity fields are not editable in the calculator. | Allow editing of base price and quantity directly in the calculator. | High | Explicitly requested; without editable fields the calculator is read-only and unusable for estimates. | Make base price and quantity cells inline-editable. Add input validation (positive numbers only). Persist changes to the project's estimate record. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | The cost calculator is a core V1 tool (Fase 3). Editable price/quantity fields are a fundamental requirement for any functional estimator. | updateLine() in components/estimating/contractor-calculator.tsx (~L52-56) makes quantity and unitPrice inline-editable.
B-05 | Changelog PDF | Cost Calculator > Contractor Info | Contractor section shows project-level info (sq ft, bathrooms, contingency) instead of contractor-specific data. | Separate contractor data from project metadata; show contractor-specific fields in the contractor section. | Medium | UX confusion; mixing project info with contractor info leads to data entry errors. | Refactor the contractor section to show only contractor-specific fields (name, rate, scope). Move project metadata to a dedicated 'Project Info' card. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Open | V1 – In Scope | Fase 5 tracks contractor execution under the Cost-Plus model. Correct separation of contractor vs. project data is required for accurate V1 cost tracking. | Confirmed: contractor section still mixes project metadata.
B-06 | Changelog PDF | Cost Calculator > Summary View | Calculator output does not show organized sections and summaries by category. | Display the estimate with sections and category subtotals matching the team's existing estimate format. | High | Explicitly requested; the current flat list makes it hard to review estimates with clients. | Group calculator line items by category (Design, Materials, Labor, Permits, Taxes & Gov Fees, Contingency). Show a subtotal per category and a grand total. | Medium | Sprint 2 (2–3 wks) | Frontend | In Progress | V1 – In Scope | Fase 3 includes client-facing budget presentation ('Presentación de 3 propuestas + presupuesto estimado'). A categorized summary view is required for client proposal presentations. | variance-report.tsx (L71-80) shows buckets with subtotals, but no explicit Design/Materials/Labor/Permits/Taxes/Contingency category breakdown.
B-07 | Changelog PDF | Cost Calculator > Imports Section | It is unclear whether the 'imports' line reflects the materials section or a separate cost category. | Clarify what 'imports' represents and ensure it is reflected correctly in the estimate. | Medium | User confusion; ambiguous label leads to incorrect cost categorization. | Rename 'imports' to a clear label (e.g., 'Imported Materials / Shipping'). Add a tooltip explaining the category. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Label clarity in the cost calculator is a V1 UX requirement. This is a minor copy/tooltip fix that supports accurate estimate presentation. | EN: Imports tab renamed to "Imported Materials" with explainer banner (data-testid="imports-explainer") clarifying that imports merge into the Materials/Labor/Receipts buckets, not a separate cost category. File: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx. ¦ ES: Pestaña renombrada a "Materiales Importados" con banner explicativo (data-testid="imports-explainer") que aclara que los imports se fusionan en los baldes de Materiales/Mano de Obra/Recibos, no son una categoría aparte. Archivo: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx.
B-08 | Changelog PDF | Cost Calculator > Effective Rate | It is unclear what 'effective rate' means in the calculator. | Clarify or remove the 'effective rate' field; add a tooltip or explanation. | Low | Minor UX confusion; a tooltip or label change resolves it. | Add an info tooltip to the 'Effective Rate' field explaining the formula. If the field is unused, remove it from the UI. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor UX polish on an existing V1 calculator field. No new feature scope required. | EN: Keyboard-focusable "?" button on the labor-baseline panel (data-testid="effective-rate-tooltip") + Effective Price tooltip on calculator explain how the effective hourly rate is computed (3 most-recent receipts ÷ hours, or last CSV import). File: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx + pages/calculator.tsx. ¦ ES: Botón "?" enfocable por teclado en el panel de línea base de mano de obra (data-testid="effective-rate-tooltip") + tooltip Precio Efectivo en la calculadora explican cómo se calcula la tarifa efectiva por hora (3 recibos más recientes ÷ horas, o último CSV). Archivo: artifacts/konti-dashboard/src/components/estimating/imports-panel.tsx + pages/calculator.tsx.
B-09 | Changelog PDF | Cost Calculator > Receipts / Variance | The variance tab is hard to find; users cannot easily navigate to receipts and categorize them. | Surface the variance/receipts tab from the dashboard so users do not need to navigate deep into the project. | Medium | Explicitly requested; discoverability issue reduces adoption of the receipts feature. | Add a 'Receipts & Variance' shortcut card on the project dashboard. Deep-link directly to the calculator variance tab. Add breadcrumb navigation. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | Fase 3 includes 'Envío de comparación real vs. estimado'. The receipts/variance tab is a core V1 feature; improving its discoverability is a V1 navigation fix. | EN: Variance Snapshot card on project-detail (data-testid="variance-snapshot-link") deep-links to /calculator?projectId=…&tab=variance for one-click drill-down from the project page. File: artifacts/konti-dashboard/src/pages/project-detail.tsx. ¦ ES: Tarjeta Resumen de Variación en project-detail (data-testid="variance-snapshot-link") enlaza directo a /calculator?projectId=…&tab=variance para acceso de un clic desde la página del proyecto. Archivo: artifacts/konti-dashboard/src/pages/project-detail.tsx.
B-10 | Changelog PDF | Cost Calculator > Receipts / Variance | Receipts and contractor estimates do not persist across server restarts (in-memory only). | Persist receipts and contractor estimates to the database so they survive restarts. | Critical | Data loss bug; any server restart wipes all entered receipt data. | Migrate receipt and contractor-estimate storage from in-memory to the persistent database. Add a migration script for existing demo data. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V1 – In Scope | Data persistence is a fundamental V1 infrastructure requirement. This is a critical bug fix, not a new feature. | EN: Receipts persistence — PROJECT_RECEIPTS and PROJECT_REPORT_TEMPLATE now hydrate from loadJSON on boot and persist via saveJSON on every change, so receipts survive an api-server restart. Files: artifacts/api-server/src/routes/projects.ts + storage snapshot layer. ¦ ES: Persistencia de recibos — PROJECT_RECEIPTS y PROJECT_REPORT_TEMPLATE ahora cargan desde loadJSON al iniciar y se guardan vía saveJSON en cada cambio, sobreviviendo a un reinicio del api-server. Archivos: artifacts/api-server/src/routes/projects.ts + capa de snapshot.
B-11 | Changelog PDF | Cost Calculator > Receipt OCR | Receipt OCR is mocked; real PDF/image extraction is not implemented. | Replace mocked OCR with real PDF/image text extraction for receipts. | High | Explicitly requested; mocked OCR produces unreliable data and erodes trust. | Integrate a real OCR service (e.g., AWS Textract or Google Document AI) for receipt PDF/image uploads. Parse vendor, date, line items, and total. | High | Sprint 2–3 (3–4 wks) | Backend | In Progress | V2 – Out of Scope | The workflow does not specify automated OCR for receipts. Manual receipt entry or upload is sufficient for V1. Real OCR integration is a significant third-party dependency best deferred to V2. | Mock OCR remains in estimating.ts (~L265). Not progressed (V2).
B-12 | Changelog PDF | Cost Calculator > Report Template | PDF export does not use the saved report template; it generates a generic layout. | Use the saved report template when exporting project PDFs from the calculator. | High | Explicitly requested; clients receive inconsistently formatted reports. | Load the project's saved report template (logo, colors, section order) when generating the PDF export. Fall back to the default template if none is saved. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | Done | V1 – In Scope | Fase 3 includes client-facing PDF presentations (Presentaciones V1-V4). Branded PDF export from the calculator is a core V1 deliverable. | EN: PDF report uses saved template — renderTemplateCostReport now consumes PROJECT_REPORT_TEMPLATE[project.id] so the templated columns/header/footer drive the export instead of hard-coded defaults. File: artifacts/api-server/src/routes/projects.ts. ¦ ES: El reporte PDF usa la plantilla guardada — renderTemplateCostReport ahora consume PROJECT_REPORT_TEMPLATE[project.id] así que las columnas/encabezado/pie de la plantilla guían la exportación en lugar de valores fijos. Archivo: artifacts/api-server/src/routes/projects.ts.
B-13 | Changelog PDF | Cost Calculator > Materials Library | No 'Add Material' button on the Materials Library page; it is read-only. | Add an 'AÑADIR MATERIALES' button to allow team to add new materials to the library. | High | Explicitly requested; without this the library cannot be maintained. | Add an 'Añadir Material' button that opens a modal form (name, unit, unit price, category, supplier). Save to the materials database. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 3.1 lists 'Materiales' as a design-phase deliverable. A writable materials library is required for the cost calculator to function correctly in V1. | AddMaterialModal in artifacts/konti-dashboard/src/pages/calculator.tsx (~L24-102).
B-14 | Changelog PDF | Cost Calculator > Labor Rates | Labor rates in the calculator do not auto-update from the last 3 uploaded receipts. | Auto-update labor rate list from the most recent receipts uploaded to the materials library. | Medium | Explicitly requested; depends on real OCR (B-11) being implemented first. | After OCR processes a receipt, extract labor line items and suggest updating the corresponding rate in the Materials Library. Require user confirmation before overwriting. | Medium | Sprint 3 (3–5 wks) | Backend | Open | V2 – Out of Scope | This feature depends on real OCR (B-11), which is already classified as V2. Auto-updating labor rates from receipts is an advanced automation not present in the V1 workflow. | Confirmed: depends on B-11 (V2 OCR).
Project Report — Casa Solar Rincón
C-01 | Changelog PDF | Project Report > Punchlist Section | Report should show punchlist with photo links, categories, and items matching the team's 'Client Punch List' Excel. | Align punchlist section in the report with the team's spreadsheet: categories, items, Drive photo links, and contractor monitoring data. | High | Explicitly requested; current report punchlist is incomplete vs. the team's source-of-truth spreadsheet. | Map punchlist categories and items to match the team's Excel structure. Add a 'Photo Link' column. Include contractor monitoring summary below the punchlist. | Medium | Sprint 2 (2–3 wks) | Backend + Frontend | In Progress | V1 – In Scope | Fase 5 explicitly lists punchlist items and contractor monitoring as client deliverables. A complete punchlist in the report is a core V1 construction-phase requirement. | EN: Partial — PunchlistPanel and ContractorMonitoringSection are now mounted inside project-report.tsx so the client report shows live punchlist + contractor monitoring data. Photo-link rollup (per-project gallery of all punchlist photos) is still pending — covered by follow-up #115. ¦ ES: Parcial — PunchlistPanel y ContractorMonitoringSection están ahora montados en project-report.tsx, así el reporte del cliente muestra datos en vivo de punchlist y monitoreo de contratista. El resumen de enlaces de fotos por proyecto sigue pendiente — cubierto por la tarea de seguimiento #115.
C-02 | Changelog PDF | Project Report > Client View | Client report shows BOM (Bill of Materials) instead of category-level summaries. | Client report should show cost categories, not the raw BOM. | High | Explicitly requested; exposing BOM to clients reveals pricing details that should remain internal. | Create a separate client-facing report view that aggregates costs by category without line-item detail. Keep BOM visible only in the team view. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | In Progress | V1 – In Scope | The workflow distinguishes between internal team views and client-facing portal content across all phases. Separate client/team report views are a V1 requirement. | Report supports a variant prop but no clear client-vs-team filter that strips BOM in favor of category-only summary.
C-03 | Changelog PDF | Project Report > Phase Chart | Phase numbers appear in the report chart; they should not show numbers. | Remove phase numbers from the phase chart in the report. | Low | Minor display issue; phase numbers in the chart conflict with the punchlist numbering. | Update the phase chart component to display phase names only (no index numbers). | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor UI fix on an existing V1 report component. No new scope required. | Phase Timeline in project-report.tsx (~L387-416) renders dots/checkmarks + phase labels only — no numeric indices visible.
C-04 | Changelog PDF | Project Report > Phase Chart | Phase chart should look like the 'phase pie chart' from the team's punchlist, not a budget chart. | Replace or redesign the phase chart to match the punchlist phase-pie-chart style. | Medium | Explicitly requested; current chart type does not match the team's reporting convention. | Replace the current chart with a donut/pie chart showing phase completion percentages. Match the color palette and label style from the team's Excel punchlist chart. | Medium | Sprint 2 (2–3 wks) | Frontend | In Progress | V1 – In Scope | Fase 3 includes 'Cronograma del proyecto' and phase progress is a core client-facing metric. The chart style change is a V1 visual alignment fix. | Pie charts now used for budget breakdown and Budget-by-Phase (project-report.tsx L440-499); not yet matched to punchlist phase-pie style.
C-05 | Changelog PDF | Project Report > Weather Status | Weather status field in the report is labeled ambiguously. | Rename the field to 'Weather Status' and ensure it reflects current/recent weather data. | Low | Minor label issue; easy fix. | Rename the weather field label to 'Weather Status'. Ensure it pulls from the weather history chart data and displays the last recorded status. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor label fix on an existing V1 report field. No new scope required. | EN: Weather card on the project report uses the label "Weather Status" (was "Weather Risk") in both Key Metrics and the dedicated weather panel. File: artifacts/konti-dashboard/src/pages/project-report.tsx. ¦ ES: La tarjeta de clima en el reporte usa la etiqueta "Estado del Clima" (antes "Riesgo Climático") tanto en Métricas Clave como en el panel dedicado. Archivo: artifacts/konti-dashboard/src/pages/project-report.tsx.
C-06 | Changelog PDF | Project Report > Data Consistency | Client report data does not match the categories and information sent in the team's regular reports. | Ensure client report categories and data match the team's report format. | High | Data inconsistency between platform and team reports erodes client trust. | Audit the client report data model against the team's report template. Align category names, subtotals, and section order. Add a 'Report Template' configuration screen. | Medium | Sprint 2–3 (3–4 wks) | Backend + Frontend | Open | V1 – In Scope | The workflow includes weekly report generation (GAMMA) and client portal access to project progress. Report data consistency is a fundamental V1 quality requirement. | Confirmed: client/team report category alignment not implemented.
C-07 | Changelog PDF | Project Report > Management Fee | Management fee source is unclear; users cannot edit it from the report page. | Show where the management fee comes from and allow editing from the calculator. | Medium | Explicitly requested; fee transparency is important for client-facing reports. | Add a tooltip on the management fee line showing the formula (% of total cost). Link to the calculator where the rate can be edited. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | Fase 5 operates under the Cost-Plus model, which includes a management fee component. Fee transparency in the client report is a V1 billing requirement. | EN: Management Fee row on the project report now shows a focusable "?" tooltip with the calculation formula and an inline Edit → link to /calculator?tab=overview (calculator aliases overview→contractor so the user lands on the editable field). File: artifacts/konti-dashboard/src/pages/project-report.tsx + pages/calculator.tsx. ¦ ES: La fila de Honorarios de Administración en el reporte ahora muestra un tooltip "?" enfocable con la fórmula y un enlace Editar → en línea a /calculator?tab=overview (la calculadora redirige overview→contractor para que el usuario llegue al campo editable). Archivo: artifacts/konti-dashboard/src/pages/project-report.tsx + pages/calculator.tsx.
C-08 | Changelog PDF | Project Report > Design / Branding | Report logo is too small. | Increase the logo size in the project report. | Low | Minor design polish. | Increase the logo container height in the report header to ~60px. Maintain aspect ratio. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Brand consistency on client-facing reports is a V1 baseline requirement. This is a trivial CSS fix. | EN: Report header logo bumped from h-14/16/20 to h-20/24/28 (~80/96/112 px) so it reads clearly on print and at the top of PDF exports. File: artifacts/konti-dashboard/src/pages/project-report.tsx. ¦ ES: El logo del encabezado del reporte aumentó de h-14/16/20 a h-20/24/28 (~80/96/112 px) para verse claramente al imprimir y en exportaciones PDF. Archivo: artifacts/konti-dashboard/src/pages/project-report.tsx.
C-09 | Changelog PDF | Project Report > Design / Branding | Report uses an aggressive dark/black color palette that does not match the team's Excel color palette. | Use the KONTi Excel color palette in the report instead of the current dark theme. | Medium | Repeated; branding consistency is important for client-facing documents. | Replace the report's dark background and text colors with the KONTi brand palette. Update all chart colors to match. | Medium | Sprint 2 (2–3 wks) | Frontend | Open | V1 – In Scope | Client-facing report branding is a V1 requirement. Color palette alignment is a CSS/design-token change with no new feature scope. | Confirmed: report still uses dark-first palette, not KONTi Excel colors.
C-10 | Changelog PDF | Project Report > Report Dates | Report dates cannot be edited; generated reports cannot be accessed side-by-side for printing/download. | Allow editing of report dates and show a history of generated reports for download. | Medium | Explicitly requested; partially addressed by existing tasks. Date editing and history view still pending. | Add a date-range picker to the report header. Store each generated report as a snapshot. Display a 'Report History' panel with download links. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | In Progress | V1 – In Scope | Weekly reports are a core V1 deliverable (Fase 5). Editable dates and basic report history are required for the weekly reporting workflow. | No editable date picker / report history list in project-report.tsx yet.
C-11 | Changelog PDF | Project Report > Site Photos | No place to import site photos for the weekly report and punchlist. | Add a photo import section to the report for weekly site photos, categorized and linkable to Drive. | High | Explicitly requested; site photos are a core part of the weekly client report. | Add a 'Site Photos' section to the report. Allow bulk upload of photos with category tags. Generate Drive-compatible links. Include a photo gallery view in the PDF export. | High | Sprint 3 (3–5 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 5 lists 'inspecciones, reportes, de avance' as client deliverables. Site photos are a core part of construction progress reporting in V1. | EN: Done in #105 — Site photos in the project report: site-photos-gallery component is rendered on the project report and PHOTO_CATEGORY_OPTIONS is wired into the report's photos block so each photo carries a category label. File: artifacts/konti-dashboard/src/pages/project-report.tsx + artifacts/konti-dashboard/src/components/site-photos-gallery.tsx. ¦ ES: Hecho en #105 — Fotos de obra en el reporte del proyecto: el componente site-photos-gallery se muestra en el reporte del proyecto y PHOTO_CATEGORY_OPTIONS está conectado al bloque de fotos del reporte para que cada foto tenga etiqueta de categoría. Archivo: artifacts/konti-dashboard/src/pages/project-report.tsx + artifacts/konti-dashboard/src/components/site-photos-gallery.tsx.
C-12 | Changelog PDF | Project Report > Background | Report background is white; users want a white or light background option. | Use a white or light background for the report; optionally support a light-mode toggle. | Low | Design preference; easy CSS change. | Set the report page background to white (#FFFFFF) by default. Add a light/dark mode toggle in the report settings. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor CSS fix on an existing V1 report page. No new scope required. | EN: Added a "White background" preset (3rd state) to the report theme cycle (light → white → dark → light); legacy light preset retains sand-tinted #F4F2EE while the new white preset is pure #FFFFFF. Selection persists per project (konti.report.theme.<projectId>) and survives reload. File: artifacts/konti-dashboard/src/pages/project-report.tsx. ¦ ES: Se agregó un preset "Fondo Blanco" (tercer estado) al ciclo de temas del reporte (claro → blanco → oscuro → claro); el preset claro original mantiene su tono arena #F4F2EE mientras el nuevo preset blanco es #FFFFFF puro. La selección se guarda por proyecto (konti.report.theme.<projectId>) y persiste al recargar. Archivo: artifacts/konti-dashboard/src/pages/project-report.tsx.
AI Assistant
D-01 | Changelog PDF | AI Assistant > Persistence | AI assistant notes and updates do not persist across server restarts. | Save AI assistant notes and action updates to the database so they survive restarts. | Critical | Data loss bug; any restart wipes AI-generated notes. | Persist AI assistant conversation history and generated notes to the database. Associate records with the project and user. Load history on page mount. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V2 – Out of Scope | The V1 workflow does not include an AI assistant module. The AI assistant is not referenced in any of the 5 workflow phases. This entire feature is out of V1 scope; persistence is moot until the feature itself is scoped for V2. | EN: AI assistant persistence — PROJECT_NOTES and SPEC_EVENTS now use the same loadJSON/saveJSON snapshot, so notes and AI spec events survive a server restart. Files: artifacts/api-server/src/routes/* + storage layer. ¦ ES: Persistencia del asistente IA — PROJECT_NOTES y SPEC_EVENTS ahora usan el mismo snapshot loadJSON/saveJSON, sobreviviendo a un reinicio del servidor. Archivos: artifacts/api-server/src/routes/* + capa de almacenamiento.
D-02 | Changelog PDF | AI Assistant > Change Orders | It is unclear whether the AI assistant is the intended channel for change orders and material specs. | Define and communicate the AI assistant's role relative to change orders and specs. | Info | Product decision required: is the AI the primary channel for change orders or a supplementary tool? | Product decision required. Once decided, add contextual help text in the AI assistant explaining its scope. | TBD | TBD (needs spec) | Product | Needs Decision | V2 – Out of Scope | The V1 workflow does not include an AI assistant. Change orders in V1 are handled through the project detail and document modules. AI-assisted change orders are a V2 enhancement.
Permits
E-01 | Changelog PDF | Permits > Header Data | The legal/engineer header from the team's permit spreadsheet is not shown in the permits view. | Surface the legal and engineer header data from the team's permit Excel on the first page of the permits view. | High | Explicitly requested as 'sumamente importante'; needed for regulatory compliance documentation. | Add a 'Permit Header' section at the top of the permits page showing: project legal name, license numbers, engineers of record, and approval dates. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 is entirely dedicated to permit authorization. Legal header data is a core V1 requirement for regulatory compliance documentation. | EN: Done in #106 — Permits page now renders the legal/engineer header block above the list, mirroring the team's spreadsheet. File: artifacts/konti-dashboard/src/pages/permits.tsx. ¦ ES: Hecho en #106 — la página de Permisos ahora muestra el bloque de encabezado legal/ingeniero arriba del listado, replicando la hoja de cálculo del equipo. Archivo: artifacts/konti-dashboard/src/pages/permits.tsx.
E-02 | Changelog PDF | Permits > Type Grouping | Permits are not separated by type (PCOC, USO, Consulta de Ubicación, etc.) as in the team's Excel. | Group permits by type to match the team's Excel structure. | High | Explicitly requested; grouping by type is the team's standard workflow. | Add a permit-type taxonomy (PCOC, USO, Consulta de Ubicación, Planos, etc.). Group the permits list by type with collapsible sections. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fase 4 includes 'Preparación de permisos requeridos' and 'Presentación / ingreso de permisos requeridos'. Permit type grouping is required for the V1 permit management workflow. | EN: Done in #106 — Permits are now grouped by type (PCOC, USO, Consulta de Ubicación, etc.) with separate sections per family, matching the team's permit Excel. File: artifacts/konti-dashboard/src/pages/permits.tsx. ¦ ES: Hecho en #106 — los Permisos ahora están agrupados por tipo (PCOC, USO, Consulta de Ubicación, etc.) con secciones separadas por familia, replicando el Excel de permisos del equipo. Archivo: artifacts/konti-dashboard/src/pages/permits.tsx.
E-03 | Changelog PDF | Permits > Label | Section label reads incorrectly; should say 'Permit Documentation'. | Rename the section label to 'Permit Documentation'. | Low | Minor copy fix. | Update the section heading string to 'Permit Documentation'. Apply globally wherever the current label appears. | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Minor copy fix on an existing V1 permits page. No new scope required. | Heading 'Permit Documentation' in artifacts/konti-dashboard/src/pages/permits.tsx (L34).
E-04 | Changelog PDF | Permits > Document Distribution | It is unclear how approved final permit documents are distributed to the client or synced with Drive. | Define and implement the final document distribution flow (Drive sync, client download). | Info | Needs product decision on Drive integration scope and client download mechanism. | Product decision required. Options: (a) manual download button for client, (b) auto-sync to Drive, (c) email notification with download link. | TBD | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | Drive sync is a third-party integration not defined in the V1 workflow. A basic client download button is V1; full Drive sync is V2. This item needs a product decision to split accordingly.
E-05 | Changelog PDF | Permits > Signature & Upload Flow | It is unclear how permit documents requiring client signatures are uploaded and processed. | Clarify and implement the permit document upload and signature workflow. | Info | Needs product decision on e-signature integration vs. manual upload. | Product decision required. Options: (a) integrate an e-signature provider (DocuSign/HelloSign), (b) upload signed PDF manually. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The workflow shows 'El cliente brinda firmas y documentos requeridos' but does not specify e-signature technology. Manual PDF upload covers V1. Third-party e-signature integration (DocuSign/HelloSign) is a V2 enhancement.
Dashboard (Inicio)
F-01 | Changelog PDF | Dashboard > Activity Feed | Activity items in the dashboard feed are not clickable/linked to their detail pages. | Make activity feed items click-through to the relevant project detail. | Medium | Explicitly requested; improves navigation efficiency from the home screen. | Wrap each activity feed item in a router link pointing to the relevant project/section. Add a hover state to indicate clickability. | Low | Sprint 1–2 (1–2 wks) | Frontend | Done | V1 – In Scope | The client portal (Fase 2 onwards) requires navigable project progress. Clickable activity feed items are a basic V1 navigation requirement. | Activity feed items wrapped in router Link in artifacts/konti-dashboard/src/pages/dashboard.tsx (~L267-277).
F-02 | Changelog PDF | Dashboard > Layout | Dashboard shows aggregated stats for all projects; client home should show only the construction status card for their project. | Restructure dashboard so client home shows only active projects and recent activity; move aggregate stats inside each project. | Medium | Explicitly requested; overwhelming aggregate view reduces usability for clients. | Create a separate client home layout showing: (1) active project construction-status card, (2) recent activity for that project only. Move aggregate stats to a team-only dashboard view. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | The workflow includes 'Acceso al portal (cliente ve el avance del proyecto)' from Fase 2 onwards. A client-specific dashboard view is a core V1 portal requirement. | isClientUser branch in dashboard.tsx (~L145-235) renders client-only project + activity feed.
Team Directory
G-01 | Changelog PDF | Team Directory > Contractor Upload | No way to upload new contractors/people to the team directory. | Allow uploading new contractor profiles to the team directory. | Medium | Explicitly requested; team directory is currently read-only for contractors. | Add an 'Add Contractor' button that opens a form (name, role, company, contact, certifications). Save to the contractor directory. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V2 – Out of Scope | The V1 workflow does not include a contractor directory management module. Contractor tracking in V1 is limited to the project-level contractor monitoring report (Fase 5). A full contractor directory CRUD is a V2 HR/operations feature. | EN: Already shipped despite V2 scope — ContractorUploadModal (single + CSV modes) on the Team Directory page. File: artifacts/konti-dashboard/src/pages/team.tsx (~L69-115). ¦ ES: Ya implementado a pesar de estar en alcance V2 — ContractorUploadModal (modos individual + CSV) en la página de Directorio del Equipo. Archivo: artifacts/konti-dashboard/src/pages/team.tsx (~L69-115).
Leads / CRM
H-01 | Changelog PDF | Leads / CRM > Score Legend | Lead score values have no explanation; users do not know what the scores mean. | Add an in-page legend explaining what lead scores represent. | Medium | Explicitly requested; without context the scores are meaningless to the team. | Add a 'Score Legend' tooltip or info panel on the leads page explaining the scoring criteria (e.g., 0–40 Cold, 41–70 Warm, 71–100 Hot). | Low | Sprint 1 (< 1 wk) | Frontend | Done | V1 – In Scope | Fase 1 includes a 'CRM ligero integrado' with lead filtering. A score legend is a basic UX requirement for the V1 CRM module. | SCORE_LEGEND with bilingual ranges/colors/hints in artifacts/konti-dashboard/src/pages/leads.tsx (~L57-62).
H-02 | Changelog PDF | Leads / CRM > Page Purpose | Users are confused about whether the Leads page is a CRM or an Asana mirror. | Clarify the page's purpose and its relationship to Asana. | Info | Needs product decision on whether to build a native CRM or maintain Asana as the source of truth. | Product decision required. Add a clear page description explaining the page's purpose. If it mirrors Asana, add a link to the Asana board. | TBD | TBD (needs spec) | Product | Needs Decision | V1 – In Scope | Fase 1 defines a 'CRM ligero integrado' and 'Notificación de tareas en ASANA'. Clarifying the CRM vs. Asana relationship is a V1 product decision that must be resolved before the CRM can be used.
H-03 | Changelog PDF | Leads / CRM > Asana Integration | It is unclear how accepting a proposal in the CRM creates a new project in Asana based on a template. | Clarify and implement the Asana template-driven project creation flow from an accepted lead. | Info | Third-party integration; needs scoping and Asana API credentials. | Product decision required. Define the trigger (proposal accepted → create Asana project from template). Implement using the Asana API. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The workflow shows 'Notificación de tareas en ASANA' as an internal automation, but full bidirectional Asana API integration (template-driven project creation) is a complex third-party dependency. Basic ASANA notification is V1; full template automation is V2.
Demo Project — General
I-01 | Changelog PDF | Demo Project > Uploads | Uploads do not persist in the demo project; nothing saves after upload. | Fix upload persistence in the demo project. | Critical | Data loss bug; upload failure blocks all demo testing. | Ensure all upload endpoints write to the persistent database (not in-memory). Verify file storage path is writable and survives restarts. | Medium | Sprint 1 (1–2 wks) | Backend | In Progress | V1 – In Scope | Data persistence is a fundamental V1 infrastructure requirement. This is a critical bug fix affecting all modules across all workflow phases. | EN: Partial — demo-project upload persistence: notes, punchlist and receipts now persist across server restarts (#B-10/D-01/I-03), but document blob storage is still in-memory. Follow-up #114 will migrate doc blobs to App Storage to fully close I-01. ¦ ES: Parcial — persistencia de cargas del proyecto demo: notas, punchlist y recibos ya persisten entre reinicios (#B-10/D-01/I-03), pero el almacenamiento de blobs de documentos sigue en memoria. La tarea de seguimiento #114 migrará los blobs a App Storage para cerrar I-01.
I-02 | Changelog PDF | Demo Project > Document Categorization | No way to categorize documents by type (permits, punchlist, drawings, etc.). | Add document categorization (permits, punchlist, drawings, etc.) to the document upload flow. | High | Explicitly requested; without categories documents are unsearchable. | Add a 'Category' dropdown to the document upload modal with options: Permits, Punchlist, Drawings, Contracts, Photos, Other. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V1 – In Scope | Fases 3.1–3.3 each list specific document types (Contrato, Planos, Notas). Document categorization is required to support the multi-phase document structure in V1. | Category dropdown in UploadModal in project-detail.tsx (~L274-288).
I-03 | Changelog PDF | Demo Project > Punchlist | Punchlist does not persist across server restarts. | Save punchlist edits to the database so they survive restarts. | Critical | Data loss bug. | Migrate punchlist storage from in-memory to the persistent database. Add optimistic UI updates with server confirmation. | Medium | Sprint 1 (1–2 wks) | Backend | Done | V1 – In Scope | The punchlist is a core V1 construction-phase deliverable (Fase 5). Data persistence is a fundamental V1 infrastructure requirement. | EN: Punchlist persistence — PROJECT_PUNCHLIST is hydrated from disk on boot and saved on every change, so punchlist entries (incl. photo metadata) survive a server restart. Files: artifacts/api-server/src/routes/projects.ts. ¦ ES: Persistencia del punchlist — PROJECT_PUNCHLIST se carga desde disco al iniciar y se guarda en cada cambio, sobreviviendo a un reinicio del servidor (incluye metadatos de fotos). Archivos: artifacts/api-server/src/routes/projects.ts.
I-04 | Changelog PDF | Demo Project > Client Notifications | Auto-email to clients for signature requests is not implemented. | Automatically email clients when a document requiring their signature is sent. | Medium | Explicitly requested; manual notification is error-prone. | Integrate an email service (SendGrid/SES). Trigger a notification email when a document is marked 'Requires Client Signature'. | Medium | Sprint 3 (3–5 wks) | Backend | In Progress | V1 – In Scope | The workflow includes automated follow-up and notification emails across multiple phases (Fase 1 lead capture, Fase 2 contract, Fase 4 permit signatures). Email notifications are a V1 automation requirement. | Activity log records 'email_sent' rows (projects.ts L705/L738/L1074) but no SendGrid/SES outbound integration.
Google Drive Integration
J-01 | Changelog PDF | Drive Integration > Data Storage | Users expect project data to be stored in or synced with Google Drive. | Enable storing or syncing project data (documents, photos, reports) to Google Drive. | Info | Third-party integration requiring OAuth scopes, Drive API, and folder-structure design. | Product decision required. Define sync scope. Implement Google OAuth flow, Drive API folder creation per project, and file upload/sync endpoints. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The V1 workflow does not specify Google Drive as a storage backend. Drive links appear only as references in punchlist photo notes. Full Drive sync is a significant third-party integration deferred to V2.

## V2 Backlog
ID | Source | Area / Module | Issue Description | Requested Change / Fix | Priority | Priority Rationale | Proposed Fix | Effort | ETA | Owner | Status | Scope | Scope Rationale
Project Detail — Casa Solar Rincón
A-02 | Changelog PDF | Project Detail > Financials | No 'Gastos no facturables' (non-billable expenses) tab exists. | Add a dedicated 'Gastos no facturables' tab to the project financials section. | Medium | Explicitly requested; needed for accurate internal cost tracking vs. client billing. | Add a new tab in the project financials panel. Create a simple CRUD table for non-billable line items (description, amount, date, category). Include subtotal at the bottom. | Medium | Sprint 2–3 (3–4 wks) | Frontend + Backend | Open | V2 – Out of Scope | The workflow covers client-facing billing (Cost-Plus invoicing) but does not include an internal non-billable expense tracking module. Defer to V2 for advanced accounting features.
A-05 | Changelog PDF | Project Detail > Documents | No version history for documents; only the latest version is accessible. | Keep the latest version downloadable but maintain a history of all versions. | Medium | Explicitly requested; essential for audit trail on contracts and permits. | Implement document versioning: store each upload as a new version, display a version history dropdown, allow download of any prior version. Show 'Latest' badge on current version. | High | Sprint 3–4 (4–6 wks) | Backend + Frontend | Open | V2 – Out of Scope | The workflow does not reference document versioning or audit trails. Basic document upload/download is V1; full version history is an advanced document management feature for V2.
A-09 | Changelog PDF | Project Detail > Client Settings | Images/media in the project are not self-manageable by the client. | Allow clients to self-administer and upload images within the project. | Medium | Explicitly requested; reduces team bottleneck for media management. | Grant clients upload permission on the Photos & Media tab. Add a client-facing media management panel with upload, delete (own uploads only), and caption-edit capabilities. | Medium | Sprint 3 (3–5 wks) | Frontend | Open | V2 – Out of Scope | The workflow shows the client as a recipient of reports and a signer of documents, not as a media manager. Full client-side media self-administration goes beyond the V1 portal scope.
A-12 | Changelog PDF | Project Detail > Client Audit Log | No audit log of client actions on the platform. | Add a section logging all client actions (logins, uploads, messages, approvals). | Medium | Explicitly requested; important for accountability and dispute resolution. | Implement a server-side event log for client sessions. Surface a read-only 'Client Activity Log' table in the team admin view. | Medium | Sprint 3 (3–5 wks) | Backend + Frontend | Open | V2 – Out of Scope | The workflow does not include an audit log module. This is a compliance/governance feature that adds significant backend complexity beyond the V1 portal scope. Defer to V2.
Cost Calculator
B-11 | Changelog PDF | Cost Calculator > Receipt OCR | Receipt OCR is mocked; real PDF/image extraction is not implemented. | Replace mocked OCR with real PDF/image text extraction for receipts. | High | Explicitly requested; mocked OCR produces unreliable data and erodes trust. | Integrate a real OCR service (e.g., AWS Textract or Google Document AI) for receipt PDF/image uploads. Parse vendor, date, line items, and total. | High | Sprint 2–3 (3–4 wks) | Backend | In Progress | V2 – Out of Scope | The workflow does not specify automated OCR for receipts. Manual receipt entry or upload is sufficient for V1. Real OCR integration is a significant third-party dependency best deferred to V2.
B-14 | Changelog PDF | Cost Calculator > Labor Rates | Labor rates in the calculator do not auto-update from the last 3 uploaded receipts. | Auto-update labor rate list from the most recent receipts uploaded to the materials library. | Medium | Explicitly requested; depends on real OCR (B-11) being implemented first. | After OCR processes a receipt, extract labor line items and suggest updating the corresponding rate in the Materials Library. Require user confirmation before overwriting. | Medium | Sprint 3 (3–5 wks) | Backend | Open | V2 – Out of Scope | This feature depends on real OCR (B-11), which is already classified as V2. Auto-updating labor rates from receipts is an advanced automation not present in the V1 workflow.
AI Assistant
D-01 | Changelog PDF | AI Assistant > Persistence | AI assistant notes and updates do not persist across server restarts. | Save AI assistant notes and action updates to the database so they survive restarts. | Critical | Data loss bug; any restart wipes AI-generated notes. | Persist AI assistant conversation history and generated notes to the database. Associate records with the project and user. Load history on page mount. | Medium | Sprint 1 (1–2 wks) | Backend | In Progress | V2 – Out of Scope | The V1 workflow does not include an AI assistant module. The AI assistant is not referenced in any of the 5 workflow phases. This entire feature is out of V1 scope; persistence is moot until the feature itself is scoped for V2.
D-02 | Changelog PDF | AI Assistant > Change Orders | It is unclear whether the AI assistant is the intended channel for change orders and material specs. | Define and communicate the AI assistant's role relative to change orders and specs. | Info | Product decision required: is the AI the primary channel for change orders or a supplementary tool? | Product decision required. Once decided, add contextual help text in the AI assistant explaining its scope. | TBD | TBD (needs spec) | Product | Needs Decision | V2 – Out of Scope | The V1 workflow does not include an AI assistant. Change orders in V1 are handled through the project detail and document modules. AI-assisted change orders are a V2 enhancement.
Permits
E-04 | Changelog PDF | Permits > Document Distribution | It is unclear how approved final permit documents are distributed to the client or synced with Drive. | Define and implement the final document distribution flow (Drive sync, client download). | Info | Needs product decision on Drive integration scope and client download mechanism. | Product decision required. Options: (a) manual download button for client, (b) auto-sync to Drive, (c) email notification with download link. | TBD | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | Drive sync is a third-party integration not defined in the V1 workflow. A basic client download button is V1; full Drive sync is V2. This item needs a product decision to split accordingly.
E-05 | Changelog PDF | Permits > Signature & Upload Flow | It is unclear how permit documents requiring client signatures are uploaded and processed. | Clarify and implement the permit document upload and signature workflow. | Info | Needs product decision on e-signature integration vs. manual upload. | Product decision required. Options: (a) integrate an e-signature provider (DocuSign/HelloSign), (b) upload signed PDF manually. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The workflow shows 'El cliente brinda firmas y documentos requeridos' but does not specify e-signature technology. Manual PDF upload covers V1. Third-party e-signature integration (DocuSign/HelloSign) is a V2 enhancement.
Team Directory
G-01 | Changelog PDF | Team Directory > Contractor Upload | No way to upload new contractors/people to the team directory. | Allow uploading new contractor profiles to the team directory. | Medium | Explicitly requested; team directory is currently read-only for contractors. | Add an 'Add Contractor' button that opens a form (name, role, company, contact, certifications). Save to the contractor directory. | Medium | Sprint 2 (2–3 wks) | Frontend + Backend | Done | V2 – Out of Scope | The V1 workflow does not include a contractor directory management module. Contractor tracking in V1 is limited to the project-level contractor monitoring report (Fase 5). A full contractor directory CRUD is a V2 HR/operations feature. | EN: Already shipped despite V2 scope — ContractorUploadModal (single + CSV modes) on the Team Directory page. File: artifacts/konti-dashboard/src/pages/team.tsx (~L69-115). ¦ ES: Ya implementado a pesar de estar en alcance V2 — ContractorUploadModal (modos individual + CSV) en la página de Directorio del Equipo. Archivo: artifacts/konti-dashboard/src/pages/team.tsx (~L69-115).
Leads / CRM
H-03 | Changelog PDF | Leads / CRM > Asana Integration | It is unclear how accepting a proposal in the CRM creates a new project in Asana based on a template. | Clarify and implement the Asana template-driven project creation flow from an accepted lead. | Info | Third-party integration; needs scoping and Asana API credentials. | Product decision required. Define the trigger (proposal accepted → create Asana project from template). Implement using the Asana API. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The workflow shows 'Notificación de tareas en ASANA' as an internal automation, but full bidirectional Asana API integration (template-driven project creation) is a complex third-party dependency. Basic ASANA notification is V1; full template automation is V2.
Google Drive Integration
J-01 | Changelog PDF | Drive Integration > Data Storage | Users expect project data to be stored in or synced with Google Drive. | Enable storing or syncing project data (documents, photos, reports) to Google Drive. | Info | Third-party integration requiring OAuth scopes, Drive API, and folder-structure design. | Product decision required. Define sync scope. Implement Google OAuth flow, Drive API folder creation per project, and file upload/sync endpoints. | High | TBD (needs spec) | Product + Backend | Needs Decision | V2 – Out of Scope | The V1 workflow does not specify Google Drive as a storage backend. Drive links appear only as references in punchlist photo notes. Full Drive sync is a significant third-party integration deferred to V2.

## Summary
KONTi Dashboard — Feedback Summary
Total Feedback Items: 57
Scope | Count
V1 – In Scope | 44
V2 – Out of Scope | 13
By Priority | V1 | V2
Critical | 3 | 1
High | 19 | 1
Medium | 13 | 6
Low | 7 | 0
Info | 2 | 5
By Status | Count
Open | 9
In Progress | 10
Done | 31
Needs Spec | 0
Needs Decision | 7
By Section / Module | V1 Items | V2 Items
Cost Calculator | 12 | 2
Project Detail — Casa Solar Rincón | 9 | 4
Project Report — Casa Solar Rincón | 12 | 0
Permits | 3 | 2
Demo Project — General | 4 | 0
Leads / CRM | 2 | 1
AI Assistant | 0 | 2
Dashboard (Inicio) | 2 | 0
Team Directory | 0 | 1
Google Drive Integration | 0 | 1
Audit snapshot (2026-04-30)
Source | gmena83/Arch-Firm-Hub @ main
Done | 31
In Progress | 10
Open | 9
Needs Decision | 7
Previous snapshot (2026-04-29)
Done | 16
In Progress | 16
Open | 18
Needs Decision | 7

## Legend & Guide
Field | Description | Example / Notes
ID | Unique item identifier. Letter = section, number = item within section. | A-01, B-03, J-01
Source | Which feedback document the item originates from. | Changelog PDF
Area / Module | The specific page, section, or feature affected. | Cost Calculator > CSV Import
Issue Description | Plain-language description of the observed problem. | CSV import fails due to column mismatch.
Requested Change / Fix | What the reviewer explicitly asked for. | Fix CSV import to accept team's estimate format.
Priority | Severity/urgency rating (see scale below). | Critical / High / Medium / Low / Info
Priority Rationale | Why this priority was assigned. | Mentioned by 3 users; blocks core estimate workflow.
Proposed Fix | Recommended technical approach for the dev team. | Add column-mapping step to CSV import flow.
Effort | Rough implementation effort: Low / Medium / High / TBD. | Low = <4 hrs ¦ Medium = 4–16 hrs ¦ High = 16+ hrs
ETA | Suggested sprint/week target for completion. | Sprint 2 (2–3 wks)
Owner | Suggested team or role responsible. | Frontend / Backend / Product
Status | Current state of the item. | Open / In Progress / Done / Needs Spec / Needs Decision
Scope | Whether the item falls within the V1 project scope defined in the 2026 workflow. | V1 – In Scope / V2 – Out of Scope
Scope Rationale | Which workflow phase or decision drives the scope classification. | Fase 4 requires client document upload for permit authorization.
PRIORITY SCALE
Critical | Blocks core functionality or causes data loss. Fix immediately. | Upload persistence, punchlist data loss
High | Significantly impairs a key workflow or repeated across multiple sessions. | CSV import, client invoice columns, photo section
Medium | Noticeable issue but has a workaround; fix in near-term sprints. | Non-billable tab, contractor section UX
Low | Minor polish or nice-to-have; fix when capacity allows. | Logo size, label copy, color tweaks
Info | Requires a product/strategic decision before dev work can begin. | Drive integration, Asana sync, e-signatures
STATUS SCALE
Open | Not yet started.
In Progress | Actively being worked on or tracked by an existing task.
Done | Shipped and verified.
Needs Spec | Requires a detailed specification before development.
Needs Decision | Requires a product or business decision before any work begins.
SCOPE SCALE
V1 – In Scope | Item maps to a feature or automation explicitly defined in the KONTi 2026 Workflow (Fases 1–5). Should be addressed in the current development cycle.
V2 – Out of Scope | Item requires a capability NOT defined in the V1 workflow (e.g., Drive sync, AI assistant, OCR, e-signatures, version history). Deferred to the next major version.